## Slide 1: Project Management: Some Nuggets and Perspective June 6, 2018
EFCOG Annual Meeting
Paul Bosco, PE, PMP, CFM, LEED-AP
Director, DOE Project Management

## Slide 2
$109 Billion

## Slide 3
$90 Billion+

## Slide 4
$2.5 Billion (7%+)

## Slide 5
$1.3 Billion (<1%)

## Slide 6
$20 Million
vs.
$6 Million

## Slide 7
$28 Billion  $34 Billion

## Slide 8: > $50 Million DOE Order 413.3B Reform (Chg 4)
Chart: Percent Success
| FY08-10 | FY09-11 | FY10-12 | FY11-13 | FY12-14 | FY13-15 | FY14-16
DOE Target
$10M-$50M | 0.8 | 0.88 | 0.93 | 0.85 | 0.77 | 0.74 | 0.9
$50M-$100M
$100M-$750M
>$750M
DOE Success Goal – 90% – Projects < $50M*
* Starting in FY18, (33) projects valued at $923M were removed from the portfolio.
1
2

## Slide 9: Major System Projects1 (>$750M)
EM, Waste Treatment & Immobilization Plant (WTP)2 – Hanford, WA ($16.813B)
1a. Direct Feed Low Activity Waste (DFLAW) Segment of Work ($8.34B)
NA, Mixed Oxide Fuel Fabrication Facility (MOX) – Savannah River, SC ($4.857B)
EM, Salt Waste Processing Facility (SWPF) – Savannah River, SC ($2.322B)
EM, River Corridor Closure Project (RCCP) – Richland, WA ($1.850B)
5a. NA, Uranium Processing Facility (UPF) Main Processing Bldg (MPB) – Oak Ridge, TN ($4.732B)3
5b. NA, Uranium Processing Facility (UPF) Salvage & Accountability Bldg (SAB) – Oak Ridge, TN ($1.18B)3
NA, Chemistry and Metallurgy Research Replacement (CMRR)4 – LANL (CD-1 Range: $2.4B - $2.9B)
Status
Notes: 1. The above listing does not include three SC Projects with PME authority delegated to SC.
2. Linked to Low Activity Waste Pretreatment System (LAWPS) Project, CD-1 Range: $220M-$470M.
3. Of seven UPF subprojects, only two (Main Processing Bldg and Salvage & Accountability Building) are greater than $750M.
4. Each CMRR subproject ((6) each) is less than $750M; in aggregate, at $2.9B (CD-1 top end of range).
Legend:
Meet Budget
Potential Breach
Will Breach
Green; was Red

## Slide 10: Major System Projects1 (>$750M)
FE, Strategic Petroleum Reserve, Life Extension Phase 2 (SPR-LE2) – Five Locations -- LA (3) and TX (2) (CD-1 Range: $750M - $1.4B)
FE, Strategic Petroleum Reserve, Marine Terminal Enhancements (SPR-MTE) – Two Locations in TX (CD-0 Range: $0.5B - $1.5B)
NA, Plutonium Modular Approach (PMA) – LANL (CD-0 Range: $1.3B - $3B)
NA, Trusted Microsystems Capability (TMC) – SNL (CD-0 Range: $900M - $3.7B)
NA, Matter-Radiation Interactions in Extremes (MaRIE) – LANL (CD-0 Range: $1.9B - $3.7B)
NA, Domestic Uranium Enrichment (DUE) – TBD (CD-0 Range: $3.3B - $14.1B)
EM, Calcine Disposition Project – INL (CD-0 Range: $2B - $16B)
SC, U.S. ITER Project – France (CD-1R Range: $4.7B - $6.5B)
Notes: 1. The above listing does not include three SC Projects with PME authority delegated to SC:
Linac Coherent Light Source II (LCLS-II) – SLAC ($1.045B), CD-2/3.
Long Baseline Neutrino Facility (LBNF) – FNAL (CD-1R Range: $1.26B-$1.86B), CD-3A ($308M).
Advanced Photon Source-Upgrade (APS-U) – ANL (CD-1 Range: $700M - $1B), CD-3A ($89.5M).

## Slide 11: Thank You! We Have Made Great Strides
Enhanced Analysis of Alternatives (AoA)
Improved technology readiness
Matured designs, particularly on nuclear projects
Improved Independent Cost Estimates (ICEs)
Aligned contract incentives
Established Department-wide Project Peer Reviews (PPRs)
Augmented Federal project teams (i.e., USACE)
Strengthened ESAAB, along with PMRC
Refined risk management tools and techniques

## Slide 12: Project Management Success Metrics – DOE vs. PMI Construction (Based on 3-Year Rolling Timeline)
Chart: Percent Success
| FY08-10 | FY09-11 | FY10-12 | FY11-13 | FY12-14 | FY13-15 | FY14-16 | FY15-17 | FY16-18
DOE | 0.75 | 0.84211 | 0.86957 | 0.83721 | 0.81579 | 0.83333 | 0.91304 | 0.88235 | 0.92
PMI | 0.41667 | 0.44737 | 0.54348 | 0.62791 | 0.71053 | 0.75 | 0.82609 | 0.82353 | 0.82
DOE Target
* Success metrics differ: 1) DOE: complete at scope, 110% of cost; 2) Project Management Institute (PMI): complete at scope, cost, and schedule, with goal of 80%.
DOE Success Goal – 90%

## Slide 13: What Can We Do Better?
Start-up and commissioning – Smoother transition from construction
IMS – Integrated Master Schedules – Developing and Using
Earned Value Management Systems (EVMS)
  NDIA versus EFCOG
  Data Analytics and “Disruptive Technologies”

## Slide 14: EVMS – Ask What not How
What: Provide accurate IT-accessible project EAC’s* monthly based on project control data analytics.
Enhanced Client / Service Provider Interface
* EAC’s – Estimates at Completion

## Slide 15: Refer to the GAO Guides (“Consistent with methods and best practices…”)
ABBA Consulting | Association for the Advancement of Cost Engineering | BAE Systems | Business Growth Solutions Ltd. | Center for Naval Analysis | CGI Federal | Comcast | Data Systems Analysts Inc. | David Consulting Group | Defense Contract Management Agency | Defense Acquisition University | Department of Defense | Department of Homeland Security | Department of Homeland Security, Domestic Nuclear Detection Office | Department of Treasury | Federal Aviation Administration | Fleming Management Consultancy | Galorath Incorporated | Hulett & Associates LLC | Hutchins & Associates | Independent Consultant | Internal Revenue Service | KM Systems Group | Lockheed Martin Corporation | Ludwig Consulting Services LLC | Management Concepts | MCR Federal LLC | Missile Defense Agency | MITRE | MITRE and National Oceanic and Atmospheric Administration | National Aeronautics and Space Administration | National Geospatial Intelligence Agency | Northrup Grumman | Office of Management and Budget | Parsons | PRICE Systems | Project and Program Management Systems, International | PT Mitratata Citragraha | Robbins Gioia | Social Security Administration | SRA Technologies | SRS Technologies | The Analytical Sciences Corporation | Technomics | Tecolote Research, Incorporated | United Kingdom Ministry of Defense | University of Colorado | U.S. Air Force, Air Force Cost Analysis Agency | U.S. Army, Army Cost Center | U.S. Army, Corps of Engineers | U.S. Navy, Center for Cost Analysis | U.S. Navy, Naval Air Systems Command | U.S. Navy, Navy Sea Systems Command | Wyle Labs

## Slide 16: Final Thought PMIAA* – What is a Program?
Direct Federal Program (aka State Department Consular Services)
Direct Federal Benefits Programs (aka VA Disability Payment Program)
State-Administered Benefit Programs (aka WIC)
Competitive Grant Programs (aka HHS Health Centers)
Block/Formula Grant Programs (aka HHS Foster Care Program)
Regulatory-based Programs (aka SBA Size Standards Program)
Capital Assets and Public Works Programs (aka Ship Building)
Information Assets Programs (aka Census Program)
Service Acquisition Programs (aka IT Services)
Credit Programs (aka Loan Guarantee Programs)
Insurance Programs (aka FDIC)
Research and Development Programs (aka Solar Energy Program)
* PMIAA – Program Management Improvement Accountability Act enacted December 2016

## Slide 17: Questions? Discussion…