## Slide 1: The World After COVID – What’s New in Project Management?
Director, Office of Project Management
Paul Bosco, PE, PMP, CFM, LEED-AP
June 21, 2023
EFCOG Working Group &
Task Team Meeting
2023

## Slide 2: Agenda
Project Management Success, and COVID Impacts
Some COVID PM Lessons Learned
DOE Order 413.3B (Program and Project Management for the Acquisition of Capital Asset Projects) Impending Actions
  DOE Order 413.3B, Change 7 – Incorporating Deputy Secretary Policy Memorandums
  Potential “Appendix E”, and Other Revisions – The Order is Opening!
4. METRR: (EVMS) Maturity & Environment Total Risk Rating
EFCOG Working Group &
Task Team Meeting
2023

## Slide 3: Project Management Success Metrics – DOE vs. PMI Construction (Based on 3-Year Rolling Timeline)
Chart: Percent Success
| FY10-12 | FY11-13 | FY12-14 | FY13-15 | FY14-16 | FY15-17 | FY16-18 | FY17-19 | FY18-20 | FY19-21 | FY20-22
DOE | 0.86957 | 0.83721 | 0.81579 | 0.83333 | 0.91304 | 0.88235 | 0.9375 | 0.89474 | 0.9 | 0.92308 | 0.94444
PMI | 0.54348 | 0.62791 | 0.71053 | 0.75 | 0.82609 | 0.82353 | 0.75 | 0.73684 | 0.8 | 0.76923 | 0.88889
DOE Target
* Success metrics differ: 1) DOE: complete at scope, 110% of cost; 2) Project Management Institute (PMI): complete at scope, cost, and schedule, with goal of 80%.
DOE Success Goal – 90%

## Slide 4: Pre-COVID vs Post-COVID Projects “At Risk” Snapshot
Chart: February 2020
| Yellow | Red
Projects | 3 | 2
Chart: December 2022
| Yellow | Red
Feb-22 | 4 | 14
$0.6B
$16.9B
$0.894B
$25B
4
2
2

## Slide 5: DOE Project Management Success: Unadjusted vs Adjusted Metric
Example: CD-2 Cost Baseline: $100 Million(M)
Baseline Change Cost Increase: + $20M
Unadjusted: $120M / $100M = 1.2, or
  20% Cost Increase: Result - Non-Success
Adjusted: $20M Cost Increase; $15M is COVID Related:
$105M / $100M = 1.05
  Adjusted 5% Cost Increase: Result - Success

## Slide 6: The COVID Impacts (The World We Knew Changed)
Workforce Challenges:
  Availability – Specific Craft Needs Difficult to Achieve
  Skillset: Journeyman Quality/Productively Lacking
  Employment Motivation Diminished
Supply Chain Timelines Protracted:
  Impacting Long Lead Procurements and More
  Basic Construction Supplies / Commodities Unavailable
  Fabrication (i.e., engineered equipment) Protracted
Economic Dynamics:
  Inflation and Construction Escalation Rates Exploded

## Slide 7: Project Management: DOE COVID Response
Workforce Challenges – The Toughest Issue to Address
  Targeted incentives for critical craft based on site specific labor market (i.e., hiring, relocation, premium pay, housing)
  Reflect reduced productivity in execution plans and risk
  Balance construction workload at sites
Expanded Use of Long Lead Procurement, (CD-3A) Actions:
  Long-lead procurement (i.e., glove boxes, magnets, etc.)
  Bulk commodities (i.e., electrical components, etc.)
Escalation Model Updated (PM Escalation Report)
  Project and site-specific adjustments; tailored weighting for craft labor, non-manual labor, materials, and subcontracts

## Slide 8: DOE Order 413.3B Change 7 - Imminent
Incorporates Past Deputy Secretary Policy Memorandums, to include:
  Lessons Learned Enhancements
  Corrective Action Plans (CAP) Approved by PME (Project Management Executive), tethered to BCP Root Cause Analysis (RCA)
  Climate Adaptation, Resilience, and Sustainability to Project Management
    Executive Order 14057

## Slide 9: DOE Order 413.3B Appendix E and More
Open for Revision this summer
Appendix E – A Key Proposal to Streamline
  Commercial-type projects, < $100M, No New Technologies, Non-Nuclear
  Consolidates Critical Decisions and Documents
Other Input Welcome for Consideration

## Slide 10: EVMS METRR -- What’s your FICO Score?
“METRR”: Maturity and Environment Total Risk Rating on Earned Value Management Systems (EVMS) – Perfection (1000 Points) is not Expected
  Maturity: (10) Sub-processes, with (56) “Attributes”
  Environment: (4) Categories (Culture, People, Practices, and Resources), with (27) “Factors”

## Slide 11: Final Result: Four Bands (N=33)
Chart: Maturity and Environment Matrix
| 711 | 823 | 858 | 570 | 544 | 730 | 816 | 857 | 729 | 734 | 703 | 511 | 810 | 707 | 725 | 627
Contractor | 735 | 684 | 730 | 686 | 530 | 705 | 723 | 891 | 794 | 556 | 800 | 544 | 897 | 516 | 783 | 701
Owner | 569 | 434 | 579 | 545 | 673 | 586 | 813 | 780 | 624 | 875 | 896
Consultant | 403 | 730 | 702 | 200 | 410 | 518 | 777 | 617
Red
Orange
Yellow
Green
Note: Score cut-offs are based on a fair data distribution across 0-1000 score scale. The sample is reduced by removing one project with no performance information and one outlier: P2 (cost growth: ~500%).

## Slide 12: Performance with Four Bands (N=33)
GREEN | 
N: | 5
Mean Cost Growth: | -0.3%
Mean Schedule Growth: | -5.9%
YELLOW | 
N: | 7
Mean Cost Growth: | +13.7%
Mean Schedule Growth: | +3.8%
ORANGE | 
N: | 15
Mean Cost Growth: | +48.2%
Mean Schedule Growth: | +26.9%
RED | 
N: | 6
Mean Cost Growth: | +92.3%
Mean Schedule Growth: | +24.3%
Note: Cost and schedule growth is measured versus the PMB at 20% project completion.
The sample is reduced by removing one project with no performance information and one outlier.
Metric | Statistical Comparison | Test | Sig.
Cost Growth (in %) | green vs. yellow vs. orange vs. red | Kruskal-Wallis | 0.007*
Schedule Growth (in %) | green vs. yellow vs. orange vs. red | Kruskal-Wallis | 0.102
*Result is significant at 0.05 level

## Slide 13: Correlation between maturity and environment scores (N=43)
To study the relationship between the maturity score and the environment score, correlation was tested.
The results showed a Pearson R value of 0.843, which indicates a strong correlation between the maturity and the environment score, with a direct or positive relationship between them (p<0.05).
Chart: Environment Score
| 403 | 735 | 684 | 730 | 686 | 569 | 434 | 530 | 730 | 702 | 579 | 705 | 545 | 673 | 200 | 586 | 723 | 410 | 896 | 891 | 518 | 794 | 617 | 556 | 800 | 544 | 701 | 813 | 897 | 624 | 777 | 875 | 516 | 783 | 780 | 597 | 431 | 358 | 678 | 489 | 539 | 264 | 564
 | 202 | 711 | 823 | 858 | 570 | 493 | 528 | 544 | 684 | 605 | 626 | 730 | 552 | 886 | 78 | 573 | 816 | 420 | 898 | 857 | 638 | 729 | 491 | 734 | 703 | 511 | 627 | 887 | 810 | 709 | 677 | 844 | 707 | 725 | 759 | 497 | 411 | 441 | 543 | 574 | 687 | 260 | 441
Maturity Score = Environment Score 0.94 + 35.89

## Slide 14
Closing Thoughts
&
Questions
EFCOG Working Group &
Task Team Meeting
2023