## Slide 1: End States Contract Model (ESCM) – Step 2
May 2019

## Slide 2: End States Contract Model (ESCM)
End State Contracting Model - Single award Indefinite Delivery/Indefinite Quantity (IDIQ) contract for each Acquisition with the ability to issue both Cost-Reimbursement (CR) and Firm-Fixed-Price (FFP) Task Orders (TO)
  Subsequent Single Sourced TO(s) = Effective Task Order Negotiations by Partnering
  Allows for Effective “Partnering”
Partnering - Open negotiations between the Contractor, Field, EM, Stakeholders, and Regulators to effectively negotiate Cost Plus Incentive Fee (CPIF) Task Order(s) for Site closure/defined End State(s) within the first 180-days

## Slide 3: End States Contract Model (ESCM)
Partnering & Negotiation Objectives (Complete within 180 days)
  Agree on scope, schedule and cost, inclusive of discussions with Regulators, as necessary
  Identify ownership of risks and mitigations
  Identify any required Government Furnished Services and Information
  Develop completion criteria and incentive fee structure (ceiling for scope of work beyond sample task period to include flat portion of CPIF Cost Curve [+/- % of cost])
  Encourage profit sharing with employees
  If cannot agree on reasonable price, re-compete the contract as minimum guarantee has been satisfied

## Slide 4: End States Contract Model (ESCM) – Current Acquisitions
  ESCM Current Acquisitions
    Central Plateau Cleanup Contract (CPCC)
    Tank Closure Contract (TCC)
    Nevada Environmental Program Services (NEPSC)
    Oak Ridge Reservation Cleanup (ORRC)
    Portsmouth Cleanup (PC)
    Idaho Cleanup Project (ICP)

## Slide 5: Steps 1 & 2 – Overview
  Step 1 – Acquisition process through Contract Award for each Site, which may include issuance of Pre-Award Task Order(s)
    “Pre-Award Task Order” – A Task Order where the Request for Task Order Proposal (RTP) was included in the Prime Contract Final RFP and evaluated prior to Award)
  Step 2 – Transition of the new contractor through the issuance of Pre-Award Task Orders and all subsequent Post Award ESC Task Orders
  Step 2a – Initial Contract Transition after Award of new Contract and issuance of remaining Year 1 Task Orders (i.e. Balance of Work (BOW) and Non-Fee bearing Task Orders (Pension, Government Furnished costs, Benefits, etc.))
  Step 2b – After Initial Contract Transition through issuance of all Post Award ESC Task Orders of the new Contract Period of Performance (POP)

## Slide 6: Step 2a – Task Order Process Flow

## Slide 7: Step 2b – Task Order Process Flow

## Slide 8: End States Contracting Teams
  End State Contracting Team (ESCT) – A Site team comprised of Federal Staff and General Support Service Contractors (GSSC) tasked to develop, coordinate, report and support all Step 2 activities and deliverables. This team will add SMEs during Step 2b based on regulatory and technical challenges.
  Site Initial Transition Team – A Site team to manage and oversee the Transition of the new and outgoing Contractor through the stated Transition period in the RFP.
  Negotiation Team – A team with a mix of Site staff and Headquarters staff which provides technical support for negotiations.

## Slide 9: Step 2 HQ Organizational Structure

## Slide 10: Step 2 Standard Site Organizational Structure

## Slide 11: Step 1 & 2 Team Roles and Responsibilities
  Step 1 – Acquisition through Contract Award and issuance of the Master IDIQ
  Team consists of EM-3, EMCBC, Site SEB, SSA and Advisors
  Responsibilities include:
    Develop Acquisition Plan
    Develop RFP
    Perform Evaluation
    Contract Award
    Issue Single Award Master IDIQ

## Slide 12: Step 1 & 2 Teams Roles and Responsibilities (cont.)
  Step 2 – Post Award Negotiated Task Order(s)
  Split into two separate distinct phases from Transition through the negotiation and issuance of all Post Award Task Orders for the New Contract Period of Performance
    Step 2a – Initial Transition Notice-to-Proceed through Transition completion
    Step 2b – After Initial Transition Phase through the end of the Contract Period of Performance

## Slide 13: Step 1 & 2 Teams Roles and Responsibilities (cont.)
Step 2a
  Ensure Site has completed workforce Transition and Year 1 work scope through issuance of Task Order(s), prior to completion of Contract Transition
  Planning/Development and Issuance of all Follow-on Task Orders covering work scope commencing after Year 1
  Issue ESC Task Orders included and evaluated in the Pre-Award phase (no more than 1 year of work)
  Issue any Non-Fee Bearing Task Orders that are Government Furnished Costs (GFC) (i.e. Pensions and Benefits) awarded at NTP
  Develop and issue Balance of Work (BOW) Task Orders that cover ongoing work that was not finished by the outgoing Contractor

## Slide 14: Step 1 & 2 Teams Roles and Responsibilities (cont.)
  Step 2b
Establish Collaborative Acquisition Integrated Project Team
Open Negotiations/Facilitate Partnering for Site closure/defined End State(s) the meet the following:
  Reduce EM Liability and Risks
  Have Regulatory Approval
  Meet EM Mission for Closure
Issue all Post Award Negotiated Task Order(s) through the remainder of the Contract POP

## Slide 15: Step 1 & 2 Teams Roles and Responsibilities (cont.)
End State Contracting Team (ESCT)
Develop all products for Step 2a and 2b and provide to Negotiation Team
Program Manager is responsible to develop all deliverables with support from Site and/or Headquarters resources
Work with Site Managers to align EM-1 Mission into Task Order(s)
Manage and maintain schedule, provide reporting to Headquarters, and support discussions with Contractor
Site Initial Transition Team
Coordinate with the ESCT on Step 2 activities and deliverables
Finish activities after deliverables required for Transition is completed by the New Contractor
Negotiation Team
Lead effort and negotiate all Post Award ESC Task Orders for Step 2a and 2b
Define End State Completion Criteria
Drive Policy and Regulatory decisions at the Site and Headquarters level
Approve Scope for Task Orders
Develop Contract and Fee structure on Task Orders

## Slide 16: Step 2a Pre-Award Activities
  Pre-Award Activities
  ESCT members assigned/designated by Site and a kickoff meetings held
  ESCT establishes weekly meetings and reporting requirements
  ESCT develops a Partnering strategy (as associated with the Task Order process) and get comments from Headquarters and Site management
  ESCT to develop a Task Order detail process, including a P6 schedule consistent with H-clause Requirements
    Task Order process will be presented to New Contractor immediately upon award
    Discussions with Contractor during kickoff meeting (Partnering) and team can negotiate the process with Contractor and both parties have an agreement to work towards
  ESCT to determine all Non-Fee Bearing Task Order(s) Required; Government Furnished Costs (GFC) (i.e. Pension, Benefits, Legacy Pensions)
    Develop and prepare Non-Fee bearing Task Order(s) Packages
    Issue all Non-Fee Bearing Task Order(s) at Award

## Slide 17: Step 2a Pre-Award Activities (cont.)
  Pre-Award Activities
  Develop IGCEs for Step 2a Post Award Task Orders
    Post Award Task Orders
      Proposals received from winning Offeror 5 days after NTP
        Requires meeting with Site management, Projects and Technical SMEs to develop Scope, define Deliverables, and Assumptions
      Task Orders are part of the current RFP
  ESCT develops all New Task Orders that will be issued to Contractor after Award including IGCEs, Task Order package, and Schedule. All Task Orders need to be ready at time of award so that issuance of the Task Order packages can be delivered to the Contractor 5 days after NTP.

## Slide 18: Initial Task Order Issuance after Contract Award
  Partnering/Kickoff of Task Order(s) (see H clause for objectives in Partnering)
  Provide Contractor Task Order templates and process to follow for Contractor review
  Set up meeting with Contractor’s Task Order team
  Hold meeting and complete the following
  Review H clause on Task Ordering Procedure
    Agree upon the Task Order Process and Templates
    Develop with Contractor - list of roles, responsibilities, objectives and goals for the Task Order process
    Agree upon Schedule for Task Order issuances provided by the Government
  Issuance of Task Orders evaluated during Pre-Award Phase
  ESCT debriefs Contractor on evaluated Task Orders
  ESCT negotiates terms of issuance of Task Orders with Contractor
  Task Orders issued to Contractor within 5 working days of NTP

## Slide 19: Initial Task Order Issuance after Contract Award
  Issuance of Task Orders for Non Fee Bearing work
  ESCT negotiates terms of issuance of Task Orders with Contractor
  Task Orders issued to Contractor within 5 working days of NTP
  Issuance of Task Orders submitted by Contractor immediately after Award
  ESCT debriefs Contractor on submitted Task Order
  Contractor provides revised proposal, if required, 2 days after debrief
  ESCT holds preliminary negotiating meeting with Contractor within
  ESCT negotiates terms of issuance of Task Orders with Contractor
  Task Orders issued to Contractor with NTP

## Slide 20: Initial Task Order Issuance after Contract Award
  Issuance of Follow-on Task Order(s) for New Work
  ESCT holds a kickoff meeting with Contractor for Follow-on Task Order(s)
  ESCT presents Task Order Package to Contractor, negotiates/explain Scope, Schedule and level of Detail Required in submission
  Contractor presents Task Order Proposal back to Government
    ESCT may need to hold other meetings for clarification or direction if required, but this does not justify an extension of the submittal of the Task Order Proposal
  Government performs modified evaluation of Task Order(s)
  ESCT negotiates Task Order with Contractor
  Awards the Task Order prior to Transition Completion

## Slide 21: Baseline Development
  Contractor Baseline Development
  ESCT holds a kickoff meeting with Contractor and reviews original Baseline submittal requirements and due dates for Task Orders evaluated during Pre-Award phase.
  Contractor to submit a BCR with all new Task Orders issued Post Award.
  DOE to review BCRs and provide comments, if any, back to Contractor prior to issuance of Task Order.
  DOE to audit Contractors baseline 30 days after Contractor takes over the Contract from the current Contractor. Review by DOE, Step 2 Team will be completed within 30 days and all comments resolved by Contractor 10 days after comments issued.

## Slide 22: Step 2b Objectives
  Step 2b Objectives
  Set up a collaborative team with established partnering agreements made up of the following:
    New Site Contractor
    EM-1 and EM-2
    Site Manager
    DOE EM Regulatory SME’s
    State and Local Regulatory Agencies
  Define each Sites vision/priorities and align with EM-1 for Contract Period of Performance
  Define achievable End States and completion criteria that reduces Liability and Risk to EM
  Work with Regulators so EM can issue Task Order for these End states with achievable completion criteria to Site Contractor
  Develop out-year planning packages with schedules, list of issues to resolve with regulators, and cost estimates that will be issued in future Task Orders as required at the Site

## Slide 23: Step 2b Deliverables
  Deliverables
  ESC Integrated Project Team (IPT) Established and Chartered
  Integrated Priority List for the POP within 6 months of Contract Award
  Partnering agreement
  Regulatory and Policy Assessment for future Task Orders
  Suggested End State and Completion Criteria Report for POP
  P6 Schedule showing issuance of all Task Orders for POP
  ESCT development of Task Order packages
  Updated PMB by Site Contractor approved by DOE
  Out-year planning packages with schedules, list of issues to resolve with regulators, and cost estimates