## Slide 1
Guide for Applying Tools Based on EVMS Concepts for Projects under $50M
Paul Tackett
CNS EVM System Surveillance Officer
Paul.Tackett@cns.doe.gov
10/20/20

## Slide 2: EFCOG Team: Project/Program Setup Up – Tailorable
Purpose
  For DOE cost reimbursed projects less than $50M where use of an EVMS is not required, define EVMS tools that provide the best value for project management
Build upon work done by NDIA Scalability Guide
Utilize inventory of tools typically used within certified EVMS
  Define key foundational tools
  Identify opportunities for tailoring based upon project size, complexity, or risk
  Include ranking and background considerations for each tool
Team Members
  Paul Tackett (CNS), Team Lead
  Matthew “Zac” West (DOE HQ)
  Lisa Cazalet (CNS)
  Chad Miller (CNS)
  Brandon Lespagnard (KCP)
  Kelly King (KCNSC)
  Scott Lasley (NNSA)
  Alex Garcia (LANL)
  Diana Neff (Sandia)

## Slide 3: EFCOG Team: Project/Program Setup Up – Tailorable
Process followed
  Team Launched October 2019 (9 meetings)
  Did not teach EVMS (NDIA duplication), requires reader know EVMS requirements typically expected in a DOE certified system
  Utilized worksheet listing EVMS tools and concepts by process group
  Ranked each tool/concept (1-5 scale) with 3 categories of project size and risk
  Defined tool/concept as: Key or Tailorable
  Assembled comments by tool/concept
  Prepared white paper guide for DOE PM-30 review
  Post as Best Practice on EFCOG website (pending)
Project Groupings
  Project less than $10M with Low Consequence
  Project between $10M and $50M with Low Risk
  Project between $10M and $50M with Higher Risk

## Slide 4: EFCOG Team: Project/Program Setup Up – Tailorable
Key versus Tailorable Concept
  Key = considered foundational to EVMS and should be incorporated in some fashion
  Tailorable = tools or concept typically associated with a fully compliant EVMS that has the most opportunity for adjustment or based upon project size and risk
Concept Scores
  Minimal Value
    None of the concepts ranked at 1 indicating there was at least some value for all concepts
  Some Value
    Significant opportunity to limit or skip this concept due to complexity or expense
  Meaningful
    Concept provides value, but may require significant effort
  Important
    Concept may include Key concepts, but adjustment of approach may be warranted based upon the project or category
  Critical
    Highest rank indicating the intent of this concept should be incorporated into management tool

## Slide 5: EFCOG Team: Project/Program Setup Up – Tailorable
Final Product
  Inventory of EVMS tools/concepts that can be utilized by a company to establish a control system for smaller projects (<$50M)
  Discussion of tool selection based upon identifying Key concepts and best value tailorable concepts