## Slide 1
Indirect Cost Analysis Roles & Responsibilities
Paul Tackett
Paul.Tackett@pxy12.doe.gov
CNS EVMS Compliance Officer
April 10, 2023

## Slide 2: Indirect Management Requirements
Indirect Mgmt: Subprocess E
GL4 (primary) OBS responsibility for management of indirects
GL8 (secondary) Integrating all time phased cost into PMB
GL13 (primary) Establish indirect budgets and allocate pools in PMB
GL19 (primary) Record indirect cost into pools consistent with budgets
Analysis Guidelines
GL24 (primary) Analyze indirect variances and communicate impact to projects
GL27 (secondary) EAC reflects expected outcome

## Slide 3: Indirect Management Roles
CAG E.4 Indirect Variance Analysis (CAG)
Pool Managers
  Establish process to analyze variances to established thresholds, and consider rate changes quarterly (E.4.1)
  Define corrective actions, which may include rate adjustments (E.4.2)
  Communicate variance information to projects, including rate changes
CAM / Project Manager
  Integrate results of indirect variance impacts into project VARs (E.4 summary)
  Reflect indirect impacts at Control Account and Project Level in VARs and EAC. (E.4.3)

## Slide 4: June 2022 EFCOG Meeting on this topic
PM-30 presented the concept of “Indirects” as an Element of Cost (EOC) at the EFCOG meeting in Washington DC
Feedback from surveillances indicate this as an area of opportunity
Presentation included “Options” to analyze indirect impacts, including grouping indirect costs for a Work Package (WP) as an EOC
Contractors at EFCOG provided feedback
Los Alamos started reflecting indirect as EOC (using Cobra)
CNS presented their solution for indirect analysis, while retaining indirects as an adder to existing EOC components
Other contractors provided input, but were not pursuing indirects as EOC
Feedback?

## Slide 5: Backup PM-30 Presentation – June 2022

## Slide 6: Direct and Indirect Control Account Analysis
Robert Loop
Project Controls Division (PM-30)
Office of Project Management (PM)
June 7, 2022

## Slide 7
Agenda
Objectives
Overview of control account variance analysis objectives
Terminology
Examples
Requirements

## Slide 8
  Objectives
Control Account Managers should be able to view the split between Direct and Indirect components of Cost Variance.
  CAMs should only develop explanations of the Direct Variances and efficiency indirect impacts.
Indirect Cost Variances can have two sources:
  The multiplication of a Direct Cost/Hours overrun
  The performance of the Indirect pools/base allocated to control accounts
Indirect Pool Performance Driver explanations should be provided to the CAMs from Finance.
Direct and Indirect analysis are the two components that add to the Control Account Totals

## Slide 9
Overview of control account variance analysis objectives
The following explanations may impact the control account:
  Direct rates (Mix) may be higher or lower than planned
  Hours may indicate that harder or easier than planned
  Similar analysis for labor, material and ODC can be performed.
  Indirect variance could be impacted by Direct or Indirect performance.
  It doesn’t take a change in Indirect Rates to have an Indirect variance impact.
  Before determining Corrective Action, the Driver of the Variance needs to be determined.
  Indirect analysis may be relevant at the control account level and not by EOC
  Real life – there are often multiple reasons for the variance within a control account.

## Slide 10
Terminology:
Labor Cost Variances
  Can be broken into “Rate Variance” vs. “Efficiency Variance”
    Rate Variance = (Earned Rate – Actual Rate) X Actual Hours
    Efficiency Variance = (Earned Hours – Actual Hours) X Earned Rate
Material Cost Variances
  Can be broken into “Price Variance” vs. “Usage Variance”
    Price Variance = (Earned Unit Price – Actual Unit Price) X Actual Quantity
    Usage Variance = (Earned Quantity – Actual Quantity) X Earned Unit Price
Indirect Cost Variances
  Can be broken into “Rate Variance” vs. “Volume Variance”
    Rate Variance = (Earned Rate – Actual Rate) X Actual Hours
    Volume Variance = (Earned Base – Actual Base) X Earned Rate

## Slide 11
  Example 1: Hours Driven Variance
Assume: Direct Rate $100, Indirect Rate 50%. Overrun by 1,000 Direct Hours
Overrun in Labor Hours Results in:
  Total of $150,000 of Cost Variance
  Overhead Volume Component = $50,000
  Direct Efficiency Component = $100,000
CAM’s Variance is to the 1000 hour Overrun, with knowledge of the Direct & Indirect Components

## Slide 12
  Example 2: Indirect Rate Driven Variance
Same planning assumptions. Overrun in Indirect Rate increased to 60%.
Overrun in Indirect Rate Results in:
  Total of $20,000 of Cost Variance
  Indirect Rate Component = $20,000
  Direct Components = $0
CAM’s Variance is Limited to an Indirect Performance explanation Provided by Finance

## Slide 13
  Example 3: Direct Rate Driven Variance
Same planning assumptions. Overrun in Direct Rate increased by $10/hour.
Overrun in Direct Rate Results in:
  Total of $30,000 of Cost Variance
  Overhead Rate Component = $10,000
  Direct Rate Component = $20,000
CAM’s Variance is to the increase in Direct Rate, with knowledge of the Direct & Indirect Components.

## Slide 14
  Example 4: Combination of Drivers
1) Hours Over by 1,000; 2) Indirect Rate increased to 60%; 3) Direct Rate over by $10/hour.
Combination of Drivers Results in:
  Total of $228,000 of Cost Variance
  Overhead Component = $98,000: Rate = $48,000, Volume = $50,000
  Direct Component = $130,000: Rate = $30,000, Efficiency = $100,000
CAM’s Variance is to the increase in Direct Rate and Hours Overrun: Indirect Rate overrun provided by Finance.

## Slide 15
Objective Expectations
Cost Accounting Standards (CAS) and related disclosure statement define overhead and G&A for the accounting system
Projects reconcile EOCs consistent with the disclosure statement definitions
Projects analyze variances in terms of root cause
Current rates or the equivalent are in the baseline and ETC/EAC.
Price / Usage is in direct units/dollars

## Slide 16
Options
Open to other options that meet the objectives
Indirect EOC for budget and actuals. Cleanest and provides method of full automation of price usage.
Indirect EOC for actuals only. Supported by reporting that breaks out indirect budget and performance separate from direct.
Indirect accounting cost elements reconciled appropriately to labor, material and ODC. Supported by reporting that breaks out indirect budget and performance and actuals separate from direct.
Key elements of all options. Direct price usage is available and understanding of direct and indirect variances at the control account level.

## Slide 17
  Summary
Only by breaking out indirect and direct analysis components can all the control account variance analysis drivers be understood.
Isolating source of Variance is critical for determining the Cause, Impact and Corrective Actions for Analysis.
Determining the Direct vs. Indirect components also allows for more accurate EAC development.
A side benefit of indirect price usage is mathematical justification of rate impacts for MR justification.
Indirect price/usage is normally limited to during a comprehensive EAC or special analysis

## Slide 18: Backup CNS Presentation – June 2022

## Slide 19: Business Need
Excerpts from (Direct and Indirect Control Account Analysis) presented by Robert Loop on June 7, 2022
“Control Account Managers should be able to view the split between Direct and Indirect components of Cost Variance.”
“Indirect Cost Variances can have two sources:
  The multiplication of a Direct Cost/Hours overrun
  The performance of the Indirect pools/base allocated to control accounts”
“Indirect Pool Performance Driver explanations should be provided to the CAMs from Finance.”
Options (slide 11)
“Key elements of all options. Direct price usage is available and understanding of direct and indirect variances at the control account level.”
Efficiency / Usage Variance
 Rate / Price Variance

## Slide 20: CNS Options to Achieve Indirect Analysis Objective
Option 1 – Segregate Indirect as EOC
Advantages:
  Indirect component of cost clearly identified at WP and CA level
Disadvantages:
  Additional analysis still required to identify the driver for changes to Indirect EOC. Changes in direct labor hours (usage) have the greatest impact on Indirect cost
  Segregating Indirect as EOC impacts existing analysis tool (Empower)
Option 2 – Demonstrate Existing Rate and Usage Analysis Tools
Advantages:
  No special programming or changes needed
  Empower provides built in analysis capability for Labor Rate / Usage components. Labor indirect cost is the only volatile component (~75% of Billed Indirect Cost)
Disadvantages:
  Indirect component of cost remains “baked in” on CPR Format 1

## Slide 21: CNS – Typical Profile of Direct & Indirect Cost
Chart: 
| Matl / SC Direct | Labor Direct | Labor Indirect | Matl / SC Indirect*
 | 3359861.57 | 764932.88 | 663679.6783 | 240716.7417
LPF FY22 period 8
(excluding fee)
*Matl / SC Indirect is a single stable procurement overhead
Chart: Indirects as Percent of Total Cost
| Labor | Matl / SC
Direct | 0.1521 | 0.66807
Indirect | 0.13197 | 0.047864
>70% of Direct cost is Material / Subcontract (stable INDIRECT component)
  Significant Price/Usage deviation for DIRECT Material defined by CAM in VAR
<30% of Direct cost is Direct Labor (more volatile INDIRECT component)
  Empower identifies labor rate/usage variances
  Accounting provides CA level feedback to explain accounting adjustments
  CAMs explain the Rate/Efficiency components in the VAR

## Slide 22: Empower – Rate / Usage Analysis
Efficiency Variance captures impact of labor hour variance
Straightforward analysis (Driver of underrun is fewer hours worked)
Rate Variance captures impact of labor rate/hour or indirect changes
Utilize dollar value of accounting provided “Rate Impact”
NO Accounting adjustment - cause is “Different resource pool used”

## Slide 23: Recommendation
Utilize Existing Tools
  Segregating Indirects as EOC adds complexity without analytical benefit
  UPF already utilizes directed custom/complex “Project Specific Indirect Rates”. Any change in handling “normal CNS Indirects” would further complicate UPF reporting.
  Existing analysis tool (Empower) relies upon fully burdened labor to generate the labor “rate” and “efficiency/usage” variances
    Rate variances driven by accounting are provided at CA level when they occur
    Rate variances driven by CAM decision on labor pool used is the only other major driver
  CNS Non-labor related Indirects are small and very stable
    Infrequent accounting provided impacts (such as year end variance distributions)
  EVM System Description requirements for Variance Analysis are currently achieved with Empower and communication of any unique accounting adjustments
Improving Indirect Visibility
  CPR Format 1 can be changed to reflect the Indirect component of cost (not additive)
  Web EVM (Cost Processor) is capable to providing custom reporting of Indirects as needed for summary analysis

## Slide 24: Questions?
COPYRIGHT NOTICE This document has been authored by Consolidated Nuclear Security, LLC, under Contract DE‑NA‑0001942 with the U.S. Department of Energy/National Nuclear Security Administration, or a subcontractor thereof. The United States Government retains and the publisher, by accepting the document for publication, acknowledges that the United States Government retains a nonexclusive, paid‑up, irrevocable, world‑wide license to publish or reproduce the published form of this document, prepare derivative works, distribute copies to the public, and perform publicly and display publicly, or allow others to do so, for United States Government purposes.
DISCLAIMER This work of authorship and those incorporated herein were prepared by Consolidated Nuclear Security, LLC (CNS) as accounts of work sponsored by an agency of the United States Government under Contract DE‑NA‑0001942. Neither the United States Government nor any agency thereof, nor CNS, nor any of their employees, makes any warranty, express or implied, or assumes any legal liability or responsibility to any non-governmental recipient hereof for the accuracy, completeness, use made, or usefulness of any information, apparatus, product, or process disclosed, or represents that its use would not infringe privately owned rights. Reference herein to any specific commercial product, process, or service by trade name, trademark, manufacturer, or otherwise, does not necessarily constitute or imply its endorsement, recommendation, or favoring by the United States Government or any agency or contractor thereof, or by CNS. The views and opinions of authors expressed herein do not necessarily state or reflect those of the United States Government or any agency or contractor (other than the authors) thereof.