## Slide 1
EVMS Self-Governance Implementation
Fluor BWXT Portsmouth
April 10, 2023

## Slide 2
Implementation of Project Health Metric
EVMS Compliance Transition to Self-Governance
  January 30, 2020 FBPORTS notified of successful demonstration of EVMS Compliance with 3 caveats
      Implement an Estimated Actuals Process
      Begin a Comprehensive EAC in 2Q FY20
      Transition to the CSV PARS reporting format by June 30, 2020
  Encourage continued partnership with PM in sharing lessons learned, continued development of consistent standards for EVMS compliance, and refinement of testing protocols and tools
  Submit Surveillance reports to PM
  Evolved and expanded our EV Checks, Project Health Checks and Schedule Metrics in support of PARS Audit Value responses

## Slide 3
Implementation of Project Health Metric
Current Self-Governance Focus
  Completion of PARS Audit Value Tests for 3 Capital Projects
      PARSID 1047 OSWDF CAP-1
      PARSID 1090 OSWDF CAP-2
      PARSID 1163 X-326 Demolition
    Currently evaluating against the 2020-02-10 Metrics
    Continue evaluation of PARS Audit Values from October, November, and December
    Complete loading of results from Automated, Hybrid, and Manual test results into an upload file

## Slide 4: Transition to PARS Audit Value Guidelines Attributes and Tests
Transition of Automated Tests dependent upon availability of new metrics in PARS Audit value test outputs.
Automated tests drive numerator and denominator
Transition to new Metrics for Manual tests can begin in the next evaluation cycle
Building of FBP Internal Independent schedule/project checks continues and will evolve with the new metrics
Begin Environmental Assessment in conjunction with Process Area Maturity in the next evaluation cycle

## Slide 5: Self-Governance
Develop Metric for completion of Self-Governance activities
  Qualitative – Meeting, Surveillance visits with CAM / Control Team, Senior Management
  Quantitative – Completion status for each Process Category Attribute metric
    Test Complete
    In-Progress
    Test Incomplete
    Frequency

## Slide 6: Thoughts
Flat File CSV to JSON
  Work with PM30 ongoing for JSON testing
Automatic Audit Vals
Schedule Health Metrics

## Slide 7: Thoughts
Flat File CSV to JSON
Started developing Flat File CSV uploads in late 2019

## Slide 8: Thoughts
Flat File CSV to JSON
  We have built the JSON within sql

## Slide 9: Thoughts
Automatic Audit Vals
  Developed to pull into sql from PM30/PARS
  Runs all automated tests on native data

## Slide 10: Thoughts
Automatic Audit Vals
  Inserts Tabs into spreadsheet with comparisons between audit val results and native data results (X/Y)
  Populates backup data in spreadsheets for reviewers so that data is readily available to formulate answers

## Slide 11: Thoughts
Schedule Health Metrics
  Cobra to P6 Checks
  P6 to P6 Checks
  Cobra Health Checks
  Overall Health Checks
  EVMS Metric Spec Automated Tests

## Slide 12: Thoughts
Schedule Health Metrics
  Information and Tests are performed daily
  Uploaded to EV NAV
  Introducing automatic email notification