## Slide 1: Project/Subproject Scheduling and JSON Export
EFCOG Project Controls Working Group 4
6/20/2023

## Slide 2: P6 JSON Effort
Sites collaborating with PM-30 and Oracle on testing
  LANL, INL, SNL, PM-30 tested exporting DOE CPP datasets from P6 (1 unique PARS ID)
  Identified anomalies and communicated with Oracle
  Sites/PM-30/Deltek/Oracle meeting on regular basis
Oracle has officially released P6 EPPM version that supports DOE CPP JSON
LANL installed P6 EPPM test environment (22.12.5)
  Identified performance issues and communicated with Oracle
  Oracle will address in next release, 22.12.7, to be released in August
Integrated Schedules
  Tested two unique projects (2 separate PARS IDs) with interproject relations
    DS exported files confirmed the external activities were generated in the datasets as SVTs
    Identified discrepancies and communicated with Oracle to address in next releases
  Tested the export of multi-subproject files with common PARS ID
    Identified issues and working with Oracle to address in next releases

## Slide 3: Cobra JSON Effort
Sites collaborating with PM-30 and Deltek on testing
LANL testing beta release of Cobra 8.5 that supports JSON export
  Generated and successfully validated initial cost DS files compared to flat files, under current Cobra configuration (WP level)
  Communicated anomalies (missing data) with Deltek and PM-30
  Will be testing under a new Cobra configuration, integrating P6 activities with Cobra (one-to-one), instead of at WP level (this is also applicable for INL)
Cobra will release version 8.5 in early July
  First official release to support DOE CPP JSON export
  Regular updates for bug fixes and enhancement to follow on a monthly basis
Sites also collaborating with PM-30, Oracle, and Deltek
  Use of Apportioned EVT
  Use of Overhead EOC

## Slide 4: White Paper Master Schedule Integration Methodology
Developed outline, received comments from subgroup 4 members
Collaborating and meeting with subgroup 4 members from various sites on development of several sections of the white paper
Addressing JSON exports and integrated project technical guidance
Development in progress, targeting end of FY23 for final version

## Slide 5: Timeline
Empower
  Encore Analytics is in the process of developing import features to support JSON files.
  Anticipated release is in late summer/early fall
P6
  Current version (22.12.5) supports JSON export with enhancement and bug fixes to be released in August (22.12.7)
  Oracle to release version 22.12.10 later this year, this version will support modifying the DOE CPP JSON template within the desktop PPM client module
Cobra
  Upcoming official release 8.5 will support JSON export, early July
DOE PM-30 targeting January 2024 as first month to receive JSON Cobra and P6 files from certain sites, LANL, and possibly other sites.
  Sites should be able to provide JSON with support from software developers
  Sites are encouraged to work with PM-30 / EFCOG on transitioning to JSON