## Slide 1: Project/Subproject Scheduling and JSON Export
EFCOG Project Controls Working Group 4
Mo Aboushousha / Brian Kong / Roy Wright
9/12/2023

## Slide 2: P6 JSON Effort
Sites collaborating with PM-30 and Oracle on testing
  Sites/PM-30/Deltek/Oracle meeting on regular basis, resolved many issues
  LANL, INL, SNL, PM-30 tested exporting DOE CPP datasets from P6 (1 unique PARS ID)
  Identified anomalies and communicated with PM-30 and Oracle
DOE released CPP DID V-5-0-0 in Mid August
  Mainly changes to Cobra output; adding DS22 (Financial Calendar), incorporating indirect flag field, and minor editorial changes
LANL P6 EPPM test environment (latest release 22.12.8)
  Has been testing since release 22.12.4
  Identified performance issues and communicated with PM-30 and Oracle
  Oracle has addressed several issues and performance enhancement in release 22.12.7
  Remaining enhancements will be addressed in release 22.12.10 (October), incorporating DID V-5-0-0
Integrated Schedules
  Tested two unique projects (2 separate PARS IDs) with interproject relationships
    DS exported files confirmed the external activities were generated in the datasets as SVTs
    Identified discrepancies (coding) and communicated with Oracle to address in next releases (22.12.10)
  Tested the export of multi-subproject files with common PARS ID
    Identified issues and working with Oracle to address in next release (EPPM 22.12.10)

## Slide 3: Cobra / Empower JSON Effort
Sites collaborating with PM-30 and Deltek on testing
LANL testing Cobra 8.5 that supports JSON export (latest release CU02)
  Generated and successfully validated files compared to flat files
  Generated and currently testing other configuration (loading Cobra at activity level – ASD)
  Communicated anomalies with PM-30 and Deltek
  Currently testing Cobra CU02 for integration with P6 22.12.8
Cobra next release CU03 and CU04
  Incorporating most of CPP DID V-5-0-0 changes and enhancements in CU03 (end of September)
  Remaining enhancements addressed in release CU04 (October)
Empower Support of JSON Import
  LANL provided two JSON datasets for testing; Cobra at WP level (TRP-III) and Cobra at activity level (ASD)
  Encore Analytics targeting release beta version that supports JSON import in fall
Sites also collaborated with PM-30, Oracle, and Deltek
  Use of Apportioned EVT (developed white paper)
  Use of Overhead EOC, changes incorporated in CPP DID 5-0-0

## Slide 4: White Paper Master Schedule Integration Methodology
White paper addresses
  Integrated master schedule best practices in a multi program/project setup
  Oracle JSON CPP export for unique PARS projects with external relationships
  Oracle JSON CPP export for combined/integrated schedules for common PARS ID (1 project)
Subgroup 4 select team members collaborated on sections of white paper
First draft is developed, currently in review by subgroup 4 select team members
Targeting end of September for PM-30 review

## Slide 5: Timeline
Empower
  Encore Analytics in process of developing import feature to support JSON files
  Anticipated release of JSON-supported Empower in fall
P6
  Current EPPM release 22.12.8 supports JSON export, incorporated enhancement and bug fixes
  Oracle EPPM release 22.12.10 (October), supports CPP JSON in desktop PPM (Pro) client module
  Oracle EPPM release 23.12.0 end of year, includes everything from 23 cloud releases
Cobra
  Upcoming releases CU03 (September) and CU04 (October), incorporating CPP DID V5-0-0
DOE PM-30 targeting January 2024 (December POP) as first month to receive JSON Cobra and P6 files from sites, LANL and select sites.
  Sites provide initial test data (November POP, reported in December) for validation in PM tools
  Sites should be able to provide JSON datasets with support from software developers
  Sites are encouraged to work with PM-30 / EFCOG on transitioning to JSON