## Instructions
EFCOG - GAO/DOE 12 Step Estimating Self-Assessment Worksheet
General Instructions for the EFCOG - GAO/DOE Cost Estimating Self-Assessment Worksheet
Version 1.2
OVERVIEW
The format of this template was originally developed by the Department of Homeland Security for life cycle cost estimates. The template has been adapted to facilitate DOE Project Management compliance with the Government Accountability Office (GAO) Cost Estimating And Assessment Guide. The worksheet is intended for use in a project teams self-assessment of the compliance of their cost estimate with the GAO Guide. The characteristics and criteria described on the following worksheet are adapted from the GAO 12 step process for achieving a high quality estimate and the four key characteristics of a high quality estimate, which can be found in the GAO Cost Estimating and Assessment Guide (GAO-09-3SP). This guide contains cost estimating best practices that have been identified by the GAO and cost experts within organizations throughout the federal government and industry. The criteria and sub-criteria used in this template were developed by leveraging the GAO Guide and the DOE Cost Estimating Guide 413.3-21A specific guidance.
Tab Name | Cell Reference/Field Name | Instructions/Description
Instructions
The intent of this template is to introduce a standard format when assessing 12-Step compliance. The template is considered a living document, whereby the participating DOE site may tailor it to meet the individual project circumstances and site requirements.
Criteria & Sub-Criteria
| Section 1 Column A Column Title: Criterion (GAO Step) | List of 12 criteria, taken from Table 2 of GAO-09-3SP, with corresponding characteristic noted.
| Section 1 Column B Column Title: GAO Chapter Number/s | Corresponding GAO Cost Estimating Guide chapter number/s to each of the individual steps.
| Section 1 Columns C-J Column Title: Sub-criterion description | These columns include the sub-criteria for each criterion, which have been adapted and modified from the 12 GAO Cost Estimating Best Practices/Steps. In order to complete a thorough assessment, each of these sub-criterion should be reviewed and assessed, in order to inform the ratings assigned to each of the criterion.
| Section 1 Column K Column Title: Practice Met? | The Cost Analyst should first rate whether each of sub-criterion is Met, Substantially Met, Partially Met, Minimally Met, or Not Met using the drop down menu. See definitions for these ratings in Section 2. The sub-criteria are denoted with a letter (e.g. (a)). Note: The rating of the sub-criteria should be completed prior to assigning a rating to the criteria (shown with a blue background and parallel to the 12 steps).
| Section 1 Column L Column Title: Status | After a rating is assigned to each sub-criterion, a color is automatically assigned based on the scoring definitions found in Section 2: Met & Substantially Met are assigned a Green Rating; Partially Met is assigned a Yellow Rating; Minimally Met & Not Met are assigned a Red Rating; Not Applicable is assigned a Grey Rating
| Section 1 Column M Column Title: Compliance Justification | Step (1c) The Cost Analyst should add an explanation of the assigned rating here using the following outline as a guide: Describe the overall results that support the ranking. Then list any particular findings concerning: (a) What was found (b) What was absent (c) Additional findings Identify elements that are critically important for the assessment; explain the effect of these issues.
| Section 1 Column N Column Title: Site Specific Reference Docs. | Step (1d) Add appropriate references to support explanation of assigned rating (i.e. document and page number(s)). Note: If the sub-criterion rating is determined to be "Not Applicable", no reference documentation is required.
| Section 1 Column O Column Title: Responsible Individual | Step (1e) If necessary, this column provides a space for identification of personnel responsible for compliance and/or approval, and additional justification or comments.
| Section 1 Column P Column Title: Reviewers Comments | Step (1f) This column provides a space for independent cost reviewer comments.
Scorecard
| Scorecard (Not yet developed) | The planned progression of this template is to have each of the 12 criterion ratings be automatically compiled and illustrated in a summary report or scorecard for an overall assessment rating of 12-Step compliance.
V1.2 (9/3/2019)

## Sub-Criteria
EFCOG - GAO/DOE 12 Step Estimating Self-Assessment Worksheet
Program/Project |  |  |  |  | Estimate Documentation File:
Date |  |  |  |  | Estimate Cost Model File:
Prepared By: |  |  |  |  | CEBD File:
Section 1
Summary of 12 GAO Cost Estimating Practices/Steps
Criterion (GAO Step) | GAO Chapter Number/s | Sub-Criterion Description |  |  |  | Practice Met? | Status | Compliance Justification | Site Specific Reference Docs. | Responsible Individual | Reviewer Comments
1) Define the estimate's purpose | 5 | Purpose. Cost estimates generally have one of the following purposes: support the budgeting process, provide a baseline for evaluation of performance or support affordability and/or comparative analysis. |  |  |  | Not Yet Rated | White
Characteristic:
Well-Documented |  | a) Determine the estimate's purpose, required level of detail and overall scope |  |  |  | Not Yet Rated | White
|  | The estimate's purpose is clearly defined |  |  |  | Not Yet Rated | White
|  | Its scope is clearly defined |  |  |  | Not Yet Rated | White
|  | The level of detail the estimate is to be conducted at is consistent with the level of detail available for the program. For example, an engineering buildup estimate should be conducted only on a well-defined program. |  |  |  | Not Yet Rated | White
|  | b) Determine who will receive the estimate |  |  |  | Not Yet Rated | White
2) Develop the estimating plan | 5 and 6 | Estimating Plan. A cost estimate should reflect a clear purpose, scope, and provide appropriate resources to develop the estimate. Specifically, documentation should address the following: |  |  |  | Not Yet Rated | White
Characteristic:
Comprehensive |  | a) Determine the cost estimating team and develop its master schedule |  |  |  | Not Yet Rated | White
|  | The estimating team's composition is commensurate with the assignment |  |  |  | Not Yet Rated | White
|  | The team has the proper number and mix of resources |  |  |  | Not Yet Rated | White
|  | Team members are from a centralized cost estimating organization |  |  |  | Not Yet Rated | White
|  | The team includes experienced and trained cost analysts |  |  |  | Not Yet Rated | White
|  | The team includes, or has direct access to, analysts experienced in the program's major areas |  |  |  | Not Yet Rated | White
|  | Team members' responsibilities are clearly defined |  |  |  | Not Yet Rated | White
|  | Team members' experience, qualifications, certifications, and training are identified |  |  |  | Not Yet Rated | White
|  | The team participated in on-the-job training, including plant and site visits |  |  |  | Not Yet Rated | White
|  | A master schedule with a written study plan has been developed |  |  |  | Not Yet Rated | White
|  | b) Determine who will do the independent cost estimate |  |  |  | Not Yet Rated | White
|  | c) Outline the cost estimating approach |  |  |  | Not Yet Rated | White
|  | The cost estimate type is clearly defined and is appropriate for its purpose |  |  |  | Not Yet Rated | White
|  | The team has access to the necessary subject matter experts |  |  |  | Not Yet Rated | White
|  | The cost estimate contains all elements suitable to its type - ICA, ICE, IGCE, LCCE, rough order of magnitude, total ownership cost: development, procurement, operating and support, disposal costs, and all sunk costs |  |  |  | Not Yet Rated | White
|  | AOA, CEA, EA, cost-benefit analysis: consistently evaluate all alternatives |  |  |  | Not Yet Rated | White
|  | EA, cost-benefit analysis: portray estimates as present values |  |  |  | Not Yet Rated | White
|  | All program costs have been estimated, including all life-cycle costs |  |  |  | Not Yet Rated | White
|  | The cost estimate is independent of funding source and appropriations |  |  |  | Not Yet Rated | White
|  | d) Develop the estimating timeline |  |  |  | Not Yet Rated | White
|  | The team has been allotted adequate time and resources to develop the estimate. |  |  |  | Not Yet Rated | White
3) Define the Program Characteristics | 7 | Program Characteristics. Critical to developing a reliable cost estimate is having an adequate understanding of the program’s key characteristics. The less such information is known, the more assumptions must be made, thus increasing the risk associated with the estimate. |  |  |  | Not Yet Rated | White
Characteristic:
Well-Documented |  | a) In a technical baseline description document, identify the program's purpose and its system and performance characteristics and all system configurations |  |  |  | Not Yet Rated | White
|  | There is a technical baseline description document |  |  |  | Not Yet Rated | White
|  | The technical baseline has been developed by qualified personnel such as system engineers |  |  |  | Not Yet Rated | White
|  | The technical baseline has been updated with technical, program, and schedule changes, and it contains sufficient detail of the best available information at any given time |  |  |  | Not Yet Rated | White
|  | The information in the technical baseline generally drives the cost estimate and the cost estimating methodology |  |  |  | Not Yet Rated | White
|  | The cost estimate is based on information in the technical baseline and has been approved by management |  |  |  | Not Yet Rated | White
|  | The technical baseline answers program related questions regarding specific requirements, purpose, technical characteristics, development plan, acquisition strategy, operational plan, and associated risks |  |  |  | Not Yet Rated | White
|  | What the program is supposed to do - requirements; |  |  |  | Not Yet Rated | White
|  | How the program will fulfill its mission - purpose; |  |  |  | Not Yet Rated | White
|  | What it will look like - technical characteristics; |  |  |  | Not Yet Rated | White
|  | Where and how the program will be built - development plan; |  |  |  | Not Yet Rated | White
|  | How the program will be acquired - acquisition strategy; |  |  |  | Not Yet Rated | White
|  | How the program will operate - operational plan; |  |  |  | Not Yet Rated | White
|  | Which characteristics affect cost the most - risk. |  |  |  | Not Yet Rated | White
|  | An affordability analysis has been performed at the agency level to see how the program fits within the overall portfolio |  |  |  | Not Yet Rated | White
|  | The agency has a process for developing cost estimates that includes the 12-step best practice process |  |  |  | Not Yet Rated | White
|  | An overall agency portfolio sand chart displays all costs for every program |  |  |  | Not Yet Rated | White
|  | b) Any technology implications |  |  |  | Not Yet Rated | White
|  | c) Its program acquisition schedule and acquisition strategy |  |  |  | Not Yet Rated | White
|  | d) Its relationship to other existing systems, including predecessor or similar legacy systems |  |  |  | Not Yet Rated | White
|  | e) Support (personnel resources, training, etc.) and security needs and risk items |  |  |  | Not Yet Rated | White
|  | f) System quantities for development, test and production |  |  |  | Not Yet Rated | White
|  | g) Deployment and maintenance plans |  |  |  | Not Yet Rated | White
4) Determine estimating structure | 8 | Estimating Structure. A WBS is the cornerstone of every program. It defines the detailed work elements needed to accomplish the program’s objectives and the logical relationship among these elements, and it provides systematic and standardized way for collecting data across the program. |  |  |  | Not Yet Rated | White
Characteristic:
Comprehensive |  | a) Define a work breakdown structure (WBS) and describe each element in a WBS dictionary (a major automated information system may have only a cost element structure) |  |  |  | Not Yet Rated | White
|  | A product-oriented WBS represents best practice |  |  |  | Not Yet Rated | White
|  | It reflects the program work that needs to be done |  |  |  | Not Yet Rated | White
|  | The WBS clearly outlines the end product and major work for the program |  |  |  | Not Yet Rated | White
|  | The WBS contains at least 3 levels indenture |  |  |  | Not Yet Rated | White
|  | The WBS is flexible and tailored to the program |  |  |  | Not Yet Rated | White
|  | The 100% rule applies: the sum of the children equals the parent |  |  |  | Not Yet Rated | White
|  | The WBS defines all work packages, which in turn include all cost elements and deliverables |  |  |  | Not Yet Rated | White
|  | In addition to hardware and software elements, the WBS contains program management and other common elements to make sure all the work is covered |  |  |  | Not Yet Rated | White
|  | The WBS is standardized so that cost data can be collected and used for estimating future programs |  |  |  | Not Yet Rated | White
|  | The WBS facilitates portfolio management, including lessons learned |  |  |  | Not Yet Rated | White
|  | The WBS matches schedule, cost estimate, and EVM at a high level |  |  |  | Not Yet Rated | White
|  | The WBS is updated as changes occur and the program becomes better defined |  |  |  | Not Yet Rated | White
|  | The WBS includes functional activities within each element that are needed to support each product deliverable |  |  |  | Not Yet Rated | White
|  | The WBS is the starting point for developing the program's detailed schedule |  |  |  | Not Yet Rated | White
|  | The WBS provides a framework for identifying and monitoring risks and the effectiveness of contingency plans |  |  |  | Not Yet Rated | White
|  | The WBS provides for a common language between the government program management office, technical specialists, prime contractors, and subcontractors |  |  |  | Not Yet Rated | White
|  | The WBS has a dictionary |  |  |  | Not Yet Rated | White
|  | The WBS defines each element and how it relates to others in the hierarchy |  |  |  | Not Yet Rated | White
|  | The WBS clearly describes what is included in each element |  |  |  | Not Yet Rated | White
|  | The WBS describes resources and functional activities needed to produce the element product |  |  |  | Not Yet Rated | White
|  | The WBS links each element to other relevant technical documents |  |  |  | Not Yet Rated | White
|  | b) Choose the best estimating method for each WBS element |  |  |  | Not Yet Rated | White
|  | Each system has one program WBS but may have several contract WBS's that are extended from the program WBS, depending on the number of subcontractors |  |  |  | Not Yet Rated | White
|  | c) Identify potential cross-checks for likely cost and schedule drivers |  |  |  | Not Yet Rated | White
|  | d) Develop a cost estimating checklist |  |  |  | Not Yet Rated | White
Criterion (GAO Step) | GAO Chapter Number/s | Sub-Criterion Description |  |  |  | Practice Met? | Status | Compliance Justification | Site Specific Reference Docs. | Responsible Individual | Reviewer Comments
5) Identify ground rules and assumptions | 9 | Ground rules and assumptions (GR&As). Cost estimates are typically based on limited information and therefore need to be bound by the constraints that make estimating possible. Among other things, these constraints should at a minimum be identified. |  |  |  | Not Yet Rated | White
Characteristic:
Well-Documented |  | a) Clearly define what the estimate includes and excludes |  |  |  | Not Yet Rated | White
|  | GR&As have been documented regarding estimating sources, historical information used, approval from management, estimating rationale, and risk |  |  |  | Not Yet Rated | White
|  | GR&As have been developed by estimators with input from the technical community |  |  |  | Not Yet Rated | White
|  | GR&As are based on information in the technical baseline document and the WBS dictionary |  |  |  | Not Yet Rated | White
|  | GR&As have been vetted and approved by upper management |  |  |  | Not Yet Rated | White
|  | GR&As have been documented to include the rationale behind the assumptions and historical data to back up any claims |  |  |  | Not Yet Rated | White
|  | GR&As are accompanied by a level of risk of each assumption's failing and its effect on the estimate |  |  |  | Not Yet Rated | White
|  | Risk mitigations have been addressed using a spreadsheet to help facilitate a risk and sensitivity analysis, and potential risks have been identified and traced to specific WBS elements |  |  |  | Not Yet Rated | White
|  | All GR&As have been placed in a single spreadsheet tab so that a risk and sensitivity analysis can be performed quickly and efficiently |  |  |  | Not Yet Rated | White
|  | All potential risks including cost, schedule, technical, and programmatic (e.g., risks associated with budget and funding, start up activities, staffing, and organizational issues) have been identified and traced to specific WBS elements |  |  |  | Not Yet Rated | White
|  | A schedule risk analysis has been performed to determine the program schedule's realism |  |  |  | Not Yet Rated | White
|  | A cost risk analysis, incorporating the results of the schedule risk analysis, has been performed to determine the program's cost estimate realism |  |  |  | Not Yet Rated | White
|  | Budget constraints, as well as the effect of delaying program content, have been defined |  |  |  | Not Yet Rated | White
|  | Peaks and valleys in time-phased budgets have been explained |  |  |  | Not Yet Rated | White
|  | Inflation index, source, and approval authority have been identified |  |  |  | Not Yet Rated | White
|  | Dependence of participating agencies, the availability of government furnished equipment, and the effects if these assumptions do not hold have been identified |  |  |  | Not Yet Rated | White
|  | Items excluded from the estimate have been documented and explained |  |  |  | Not Yet Rated | White
|  | Technology was mature before it was included; if its maturity was assumed, the estimate addresses the effect of the assumption's failure on cost and schedule |  |  |  | Not Yet Rated | White
|  | Cost estimators and auditors met with technical staff to determine risk distributions for all assumptions; the distributions were used in sensitivity and uncertainty analyses of the effects of invalid assumptions. Management has been briefed, and the results have been documented |  |  |  | Not Yet Rated | White
|  | b) Identify global and program-specific assumptions, such as the estimate's base year, including time-phasing and life cycle |  |  |  | Not Yet Rated | White
|  | c) Identify program schedule information by phase and program acquisition strategy |  |  |  | Not Yet Rated | White
|  | d) Identify any schedule or budget constraints, inflation assumptions and travel costs |  |  |  | Not Yet Rated | White
|  | e) Specify equipment the government is to furnish as well as the use of existing facilities or new modification or development |  |  |  | Not Yet Rated | White
|  | f) Identify prime contractor and major subcontractors |  |  |  | Not Yet Rated | White
|  | g) Determine technology refresh cycles, technology assumptions, and new technology to be developed |  |  |  | Not Yet Rated | White
|  | h) Define commonality with legacy systems and assumed heritage savings |  |  |  | Not Yet Rated | White
|  | i) Describe effects of new ways of doing business |  |  |  | Not Yet Rated | White
6) Obtain data | 10 | Data. Cost estimates should be rooted in historical data. |  |  |  | Not Yet Rated | White
Characteristic:
Well-Documented |  | a) Create a data plan with emphasis on collecting current and relevant technical, programmatic, cost and risk data |  |  |  | Not Yet Rated | White
|  | The estimate's data has been comprehensively analyzed, documented, and assembled |  |  |  | Not Yet Rated | White
|  | Data have been applied to the program being estimated |  |  |  | Not Yet Rated | White
|  | Data have been adequately documented as to source, content, time, units, assessment of accuracy and reliability, and circumstances affecting the data |  |  |  | Not Yet Rated | White
|  | Data were assembled as early as possible, so analysts can participate in site visits to understand the program and question data providers |  |  |  | Not Yet Rated | White
|  | b) Investigate possible data sources |  |  |  | Not Yet Rated | White
|  | Data have been gathered from historical actual cost, schedule and program, and technical sources |  |  |  | Not Yet Rated | White
|  | Data have been collected from primary sources, if possible, and secondary sources as the next best option, especially for cross-checking results |  |  |  | Not Yet Rated | White
|  | c) Collect data and normalize them for cost accounting, inflation, learning and quantity adjustments |  |  |  | Not Yet Rated | White
|  | Data have been fully reviewed to understand their limitations and risks |  |  |  | Not Yet Rated | White
|  | Data have been segregated into nonrecurring and recurring costs |  |  |  | Not Yet Rated | White
|  | Data are current and found applicable to the program being estimated |  |  |  | Not Yet Rated | White
|  | Data have been normalized to account for cost and sizing units, mission or application, technology maturity, and content so they are consistent for comparisons |  |  |  | Not Yet Rated | White
|  | Data have been normalized to constant base-year dollars to remove the effects of inflation, and the inflation index was documented and explained |  |  |  | Not Yet Rated | White
|  | d) Analyze the data for cost drivers, trends and outliers and compare results against rules of thumb and standard factors derived from historical data |  |  |  | Not Yet Rated | White
|  | Data have been segregated into nonrecurring and recurring costs |  |  |  | Not Yet Rated | White
|  | Data have been validated, using historical data as a benchmark for reasonableness |  |  |  | Not Yet Rated | White
|  | Data have been analyzed with a scatter plot to determine trends and outliers |  |  |  | Not Yet Rated | White
|  | Data have been analyzed with descriptive statistics |  |  |  | Not Yet Rated | White
|  | e) Interview data sources and document all pertinent information, including an assessment of data reliability and accuracy |  |  |  | Not Yet Rated | White
|  | f) Store data for future estimates |  |  |  | Not Yet Rated | White
|  | Data have been continually collected, protected, and stored for future use |  |  |  | Not Yet Rated | White
7) Develop point estimate and compare it to an independent cost estimate | 11, 12 and 15 | Point Estimate. A point estimate represents the sum of the most likely estimate of costs given the underlying data. |  |  |  | Not Yet Rated | White
Characteristic:
Accurate (a) |  | a) Develop the cost model, estimating each WBS element, using the best methodology from the data collected, and including all estimating assumptions |  |  |  | Not Yet Rated | White
|  | The cost estimator considered various cost estimating methods (e.g., analogy, expert opinion, build up method later, parametric, and using actual cost data) |  |  |  | Not Yet Rated | White
|  | Analogy, early in the life cycle, when little was known about the system being developed |  |  |  | Not Yet Rated | White
|  | Adjustments were based on program information, physical and performance characteristics, contract type |  |  |  | Not Yet Rated | White
|  | Expert opinion, very early in the life cycle, if an estimate could be derived no other way |  |  |  | Not Yet Rated | White
|  | Build-up method later, in acquisition, when the scope of work was well defined and a complete WBS could be determined |  |  |  | Not Yet Rated | White
|  | Parametrics, if a database of sufficient size, quality, and homogeneity was available for developing valid cost estimating relationships and the data were normalized correctly |  |  |  | Not Yet Rated | White
|  | Parametric models were calibrated and validated using historical data |  |  |  | Not Yet Rated | White
|  | Extrapolating from actual cost data, at the start of production |  |  |  | Not Yet Rated | White
|  | Cost estimating relationships (CERs) were considered |  |  |  | Not Yet Rated | White
|  | Statistical techniques were used to develop CERs |  |  |  | Not Yet Rated | White
|  | Higher R-squared |  |  |  | Not Yet Rated | White
|  | Statistical significance, for determining the validity of statistical relationships |  |  |  | Not Yet Rated | White
|  | Significance levels of F and t statistics |  |  |  | Not Yet Rated | White
|  | The cost estimator followed a CER checklist |  |  |  | Not Yet Rated | White
|  | Examined the underlying data set to understand anomalies |  |  |  | Not Yet Rated | White
|  | Checked equations to ensure logical relationships |  |  |  | Not Yet Rated | White
|  | Normalized the data |  |  |  | Not Yet Rated | White
|  | Ensured that CER inputs were within the valid dataset range |  |  |  | Not Yet Rated | White
|  | Checked modeling assumptions to ensure they applied to the program |  |  |  | Not Yet Rated | White
|  | Learning curve theory was applied for production outliers |  |  |  | Not Yet Rated | White
|  | Much manual labor was required for production |  |  |  | Not Yet Rated | White
|  | Production was continuous or adjustments had to be made |  |  |  | Not Yet Rated | White
|  | Items to be produced required complex processes |  |  |  | Not Yet Rated | White
|  | Technological change was minimal between production lots |  |  |  | Not Yet Rated | White
|  | The contractor's business process was being continually improved |  |  |  | Not Yet Rated | White
|  | Production rate and breaks in production were considered |  |  |  | Not Yet Rated | White
|  | The point estimate was developed by aggregating the WBS element cost estimates by one of the cost estimating methods |  |  |  | Not Yet Rated | White
|  | Results were checked for accuracy, double-counting, and omissions and were validated with cross-checks and independent cost estimates |  |  |  | Not Yet Rated | White
|  | The point estimate includes software purchase and/or development costs |  |  |  | Not Yet Rated | White
|  | The software cost estimate followed the 12-Step estimating process |  |  |  | Not Yet Rated | White
|  | The software sizing method was appropriate |  |  |  | Not Yet Rated | White
|  | Software costs estimates are comprehensive (e.g., labor costs, productivity factors, assumptions, and schedules) |  |  |  | Not Yet Rated | White
|  | b) Express estimate in constant year dollars |  |  |  | Not Yet Rated | White
|  | c) Time-phase the results by spreading costs in the years they are expected to occur, based on the program schedule |  |  |  | Not Yet Rated | White
|  | d) Sum the WBS elements to develop the overall point estimate |  |  |  | Not Yet Rated | White
|  | e) Validate the estimate by looking for errors like double counting and omitted costs |  |  |  | Not Yet Rated | White
|  | f) Update the model as more data become available or as changes occur and compare results against previous estimates |  |  |  | Not Yet Rated | White
Credible (b) |  | Independent Cost Estimate and Crosschecks. In order to ensure the credibility of the point estimate, it should be validated, preferably against an independent cost estimate (ICE). |  |  |  | Not Yet Rated | White
|  | g) Compare estimate against the independent cost estimate and examine where and why there are differences |  |  |  | Not Yet Rated | White
|  | h) Perform crosschecks on cost drivers to see if results are similar |  |  |  | Not Yet Rated | White
Criterion (GAO Step) | GAO Chapter Number/s | Sub-Criterion Description |  |  |  | Practice Met? | Status | Compliance Justification | Site Specific Reference Docs. | Responsible Individual | Reviewer Comments
8) Conduct sensitivity analysis | 13 | Sensitivity Analysis. A sensitivity analysis examines the effects of changing assumptions and ground rules. |  |  |  | Not Yet Rated | White
Characteristic:
Credible |  | a) Test the sensitivity of cost elements to changes in estimating input values and key assumptions |  |  |  | Not Yet Rated | White
|  | b) Identify effects on the overall estimate of changing the program schedule or quantities |  |  |  | Not Yet Rated | White
|  | c) Determine which assumptions are key cost drivers and which cost elements are affected most by changes |  |  |  | Not Yet Rated | White
|  | The cost estimate was accompanied by a sensitivity analysis that identified the effects of changing key cost driver assumption and factors |  |  |  | Not Yet Rated | White
|  | Well-documented sources supported the assumption or factor ranges |  |  |  | Not Yet Rated | White
|  | The sensitivity analysis was part of a quantitative risk assessment and not based on arbitrary plus or minus percentages |  |  |  | Not Yet Rated | White
|  | Cost-sensitive assumptions and factors were further examined to see whether design changes should be implemented to mitigate risk |  |  |  | Not Yet Rated | White
|  | Sensitivity analysis was used to create a range of best and worst case costs |  |  |  | Not Yet Rated | White
|  | Assumptions and performance characteristics listed in the technical baseline descriptions and GR&As were tested for sensitivity, especially those least understood or at risk of changing |  |  |  | Not Yet Rated | White
|  | Results were well documented and presented to management for decisions |  |  |  | Not Yet Rated | White
|  | Key cost drivers were identified |  |  |  | Not Yet Rated | White
|  | Cost elements representing the highest percentage of cost were determined and their parameters and assumptions were examined |  |  |  | Not Yet Rated | White
|  | The total cost was re-estimated by varying each parameter between its minimum and maximum range |  |  |  | Not Yet Rated | White
|  | Results were documented and the re-estimate was repeated for each parameter that was a key cost driver |  |  |  | Not Yet Rated | White
|  | Outcomes were evaluated for parameters most sensitive to change |  |  |  | Not Yet Rated | White
|  | The sensitivity analysis provided a range of possible costs, a point estimate, and a method for performing what-if analysis |  |  |  | Not Yet Rated | White
9) Conduct risk and uncertainty analysis | 14 | Risk and Uncertainty Analysis. A cost estimate is a prediction based on assumptions, constraints, and unknowns, and thus the risk exists that actual costs will differ from the estimate. To understand this risk and associated uncertainty, both should be analyzed. |  |  |  | Not Yet Rated | White
Characteristic:
Credible |  | a) Determine and discuss with technical experts the level of cost, schedule, and technical risk associated with each WBS element |  |  |  | Not Yet Rated | White
|  | b) Analyze each risk for its severity and probability |  |  |  | Not Yet Rated | White
|  | A risk and uncertainty analysis quantified the imperfectly understood risks that are in the program and identified the effects of changing key cost driver assumptions and factors |  |  |  | Not Yet Rated | White
|  | Management was given a range of possible costs and the level of certainty in achieving the point estimate |  |  |  | Not Yet Rated | White
|  | A risk adjusted estimate that reflects the program's risks was determined |  |  |  | Not Yet Rated | White
|  | Periodic risk and uncertainty analysis was conducted to improve estimate uncertainty |  |  |  | Not Yet Rated | White
|  | A cumulative probability density function, an S curve, mapped various cost estimates to a certain probability level and defensible contingency reserves were developed |  |  |  | Not Yet Rated | White
|  | c) Develop minimum, most likely, and maximum ranges for each risk element |  |  |  | Not Yet Rated | White
|  | d) Determine type of risk distributions and reason for their use |  |  |  | Not Yet Rated | White
|  | e) Ensure that risks are correlated |  |  |  | Not Yet Rated | White
|  | f) Use an acceptable statistical analysis method (e.g., Monte Carlo simulation) to develop a confidence interval around the point estimate |  |  |  | Not Yet Rated | White
|  | Credible steps were taken in perfuming an uncertainty analysis |  |  |  | Not Yet Rated | White
|  | Program cost drivers and associated risks were determined, including those relating to changing requirements, cost estimating errors, business or economic uncertainty, and technology, schedule, program, and software uncertainty |  |  |  | Not Yet Rated | White
|  | All risks were documented for source, data quality and availability, and probability and consequence |  |  |  | Not Yet Rated | White
|  | Risks were collected from staff within and outside the program to counter optimism |  |  |  | Not Yet Rated | White
|  | Uncertainty was determined by cost growth factor, expert opinion (adjusted to consider a wider range of risks), statistics and Monte Carlo simulation, technology readiness levels, software engineering maturity models and risk evaluation methods, schedule risk analysis, risk cube (P-I matrix) method, or risk scoring |  |  |  | Not Yet Rated | White
|  | A probability distribution modeled each cost element's uncertainty based on data availability, reliability, and variability |  |  |  | Not Yet Rated | White
|  | A range of values an their respective probabilities were determined either based on statistics ore expressed as 3-point estimates (best case, most likely, and worst case), and rationale for choosing the probability distributions should be provided |  |  |  | Not Yet Rated | White
|  | Documentation of the rationale for choosing the probability distributions should be provided |  |  |  | Not Yet Rated | White
|  | g) Identify the confidence level of the point estimate |  |  |  | Not Yet Rated | White
|  | h) Identify the amount of contingency funding and add this to the point estimate to determine the risk-adjusted cost estimate |  |  |  | Not Yet Rated | White
|  | i) Recommend that the project or program office develop a risk management plan to track and mitigate risks |  |  |  | Not Yet Rated | White
10) Document the estimate | 16 | Documentation. Documentation should provide an appropriate level of detail so that a cost analyst unfamiliar with the program could understand how the estimate was derived. |  |  |  | Not Yet Rated | White
Characteristic:
Well-Documented |  | a) Document all steps used to develop the cost estimate so that a cost analyst unfamiliar with the program can recreate it quickly and produce the same result |  |  |  | Not Yet Rated | White
|  | Supporting data are adequate for easily updating the estimate to reflect actual costs or program changes and using them for future estimates |  |  |  | Not Yet Rated | White
|  | The documentation is mathematically sensible and logical |  |  |  | Not Yet Rated | White
|  | b) Document the purpose of the estimate, the team that prepared it, and who approved the estimate and on what date |  |  |  | Not Yet Rated | White
|  | c) Describe the program, its schedule, and the technical baseline used to create the estimate |  |  |  | Not Yet Rated | White
|  | The documentation describes the estimate with narrative and cost tables |  |  |  | Not Yet Rated | White
|  | d) Present the program's time-phased life cycle cost |  |  |  | Not Yet Rated | White
|  | e) Discuss all ground rules and assumptions |  |  |  | Not Yet Rated | White
|  | f) Include auditable and traceable data sources for each cost element and document for all data sources how the data were normalized |  |  |  | Not Yet Rated | White
|  | g) Describe in detail the estimating methodology and rationale used to derive each WBS element's cost (prefer more detail over less) |  |  |  | Not Yet Rated | White
|  | The estimate contains an executive summary, introduction, and descriptions of methods, with data broken out by WBS cost elements, sensitivity analysis, risk and uncertainty analysis, management approval, and updates that reflect actual costs and changes |  |  |  | Not Yet Rated | White
|  | Detail addresses best practices and the 12 steps of high-quality estimates |  |  |  | Not Yet Rated | White
|  | h) Describe the results of the risk, uncertainty, and sensitivity analyses and whether any contingency funds were identified |  |  |  | Not Yet Rated | White
|  | i) Document how the estimate compares to the funding profile |  |  |  | Not Yet Rated | White
|  | The estimate discusses contingency reserves and how they were derived from risk and uncertainty analysis and the life cycle cost estimate funding profile |  |  |  | Not Yet Rated | White
|  | j) Track how this estimate compares to any previous estimates |  |  |  | Not Yet Rated | White
Criterion (GAO Step) | GAO Chapter Number/s | Sub-Criterion Description |  |  |  | Practice Met? | Status | Compliance Justification | Site Specific Reference Docs. | Responsible Individual | Reviewer Comments
11) Present estimate to management for approval | 17 | Presenting the Estimate. A briefing should be prepared for management that contains enough detail to show that the estimate is accurate, complete, and reliable, and management should approve the estimate. |  |  |  | Not Yet Rated | White
Characteristic:
Well-Documented |  | a) Develop a briefing that presents the documented cost estimate |  |  |  | Not Yet Rated | White
|  | The briefing is simple, clear, and concise enough to convey its level of competence |  |  |  | Not Yet Rated | White
|  | The briefing is consistent, allowing management to focus on the estimate's content |  |  |  | Not Yet Rated | White
|  | The briefing contains a title page, outline, and brief statement regarding the estimate's purpose |  |  |  | Not Yet Rated | White
|  | The briefing includes a discussion of the GR&As, and any other concerns or challenges |  |  |  | Not Yet Rated | White
|  | The briefing contains conclusions and recommendations |  |  |  | Not Yet Rated | White
|  | b) Include an explanation of the technical and programmatic baseline and any uncertainties |  |  |  | Not Yet Rated | White
|  | The briefing contains an overview of the program's technical foundation and objectives |  |  |  | Not Yet Rated | White
|  | c) Compare the estimate to an independent cost estimate (ICE) and explain any differences |  |  |  | Not Yet Rated | White
|  | d) Compare the estimate (life-cycle cost estimate (LCCE)) or independent cost estimate to the budget with enough detail to easily defend it by showing how it is accurate, complete, and high in quality |  |  |  | Not Yet Rated | White
|  | The briefing contains LCCE results in time-phased constant-year dollars, tracked to previous estimates |  |  |  | Not Yet Rated | White
|  | The briefing contains the method and process for each WBS cost element, with estimating techniques and data sources |  |  |  | Not Yet Rated | White
|  | The briefing contains the comparison of the point estimate to an ICE with discussion of differences and whether the point estimate was reasonable |  |  |  | Not Yet Rated | White
|  | e) Focus in a logical manner on the largest cost elements and cost drivers |  |  |  | Not Yet Rated | White
|  | f) Make the content clear and complete so that those who are unfamiliar with it can easily comprehend the competence that underlies the estimate results |  |  |  | Not Yet Rated | White
|  | g) Make backup slides available for more probing questions |  |  |  | Not Yet Rated | White
|  | The briefing illustrates the largest cost drivers, presenting them logically, with backup charts for responding to more probing questions |  |  |  | Not Yet Rated | White
|  | The briefing contains the results of sensitivity analysis and cost drivers that were identified |  |  |  | Not Yet Rated | White
|  | The briefing contains the results of risk and uncertainty analysis with confidence interval, S curve analysis, and bounds and distributions |  |  |  | Not Yet Rated | White
|  | The briefing contains an affordability analysis based on funding and contingency reserves |  |  |  | Not Yet Rated | White
|  | h) Act on and document feedback from management |  |  |  | Not Yet Rated | White
|  | Feedback from the briefing, including management's acceptance of the estimate, was acted on and recorded in the cost estimate documentation |  |  |  | Not Yet Rated | White
|  | i) Request acceptance of the estimate |  |  |  | Not Yet Rated | White
12) Update the estimate to reflect actual costs and changes | 16, 18, 19 and 20 | Update the Estimate. The cost estimate should be updated to ensure that it is current. |  |  |  | Not Yet Rated | White
Characteristic:
Accurate |  | a) Update the estimate to reflect changes in technical or program assumptions or keep it current as the program passes through new phases or milestones |  |  |  | Not Yet Rated | White
|  | The estimate is updated as actual costs become available from the EVM system or requirements change |  |  |  | Not Yet Rated | White
|  | b) Replace estimates with EVM EAC and independent estimate at completion (EAC) from the integrated EVM system |  |  |  | Not Yet Rated | White
|  | Authorized changes to the EVM performance measurement baseline were incorporated in a timely manner |  |  |  | Not Yet Rated | White
|  | It reflected current requirements |  |  |  | Not Yet Rated | White
|  | These changes were incorporated in a documented, disciplined, and timely manner so that budget, schedule, and work stayed together for true performance measurement |  |  |  | Not Yet Rated | White
|  | Changes were approved and implemented in a well-defined baseline control process |  |  |  | Not Yet Rated | White
|  | c) Report progress on meeting cost and schedule estimates |  |  |  | Not Yet Rated | White
|  | Regular EVM system surveillance ensued the contractor's effective management of cost, schedule, and technical performance and compliance with ANSI guidelines |  |  |  | Not Yet Rated | White
|  | The surveillance organization was independent and had authority to resolve issues |  |  |  | Not Yet Rated | White
|  | Surveillance staff had good knowledge about EVM and agency programs |  |  |  | Not Yet Rated | White
|  | An annual surveillance plan was developed and programs were chosen effectively |  |  |  | Not Yet Rated | White
|  | Findings and recommendations were presented to the program team for clarification, and the final surveillance report had an action plan to resolve findings quickly |  |  |  | Not Yet Rated | White
|  | The contractor's over target baseline or over target schedule was detailed, reasonable, and realistic; planned for costs, schedule, and management review; and described measures in place to prevent another OTB |  |  |  | Not Yet Rated | White
|  | Updated EACs and other EVM data were continually reported to management |  |  |  | Not Yet Rated | White
|  | EVM and CSFR-like data were examined regularly to identify problems and act on them quickly |  |  |  | Not Yet Rated | White
|  | d) Perform a post mortem and document lessons learned for elements whose actual costs or schedules differ from the estimate |  |  |  | Not Yet Rated | White
|  | Post mortems and lessons learned are continually documented |  |  |  | Not Yet Rated | White
|  | Actual cost, technical, and schedule data were archived for future use |  |  |  | Not Yet Rated | White
|  | e) Document all changes to the program and how they affect the cost estimate |  |  |  | Not Yet Rated | White
Section 2
Definitions/Rules
Definitions: | The Cost Analyst will select a quality description for the detailed report using the following guidance (consistent with GAO subjective definition):
Ø Not Met = Estimate provides no evidence that satisfies any portion of the criterion/sub-criterion
Ø Minimally Met = Estimate provides evidence that satisfies less than one-half of the criterion/sub-criterion
Ø Partially Met = Estimate provides evidence that satisfies approximately one-half of the criterion/sub-criterion
Ø Substantially Met = Estimate provides evidence that satisfies greater than one-half of the criterion/sub-criterion; of the missed criterion/sub-criterion, if one is a critical issue the Cost Analyst will down grade ranking to Not Met, Minimally Met, or Partially Met
Ø Met = Estimate provides complete evidence that satisfies the entire criterion/sub-criterion
Sub-Criterion Rating Rules: | If the sub-criterion descriptions above contain multiple items, each should be addressed when assigning a rating and providing justification.
For example, item 2 (a) - "The documentation should include… The estimating team and its master schedule"
If the documentation identifies the team members, but does not contain a master schedule, this item should be rated as "Partially Met"
Sample Justification: "The master schedule will be completed when the program identifies the project's priority"
Criterion Rating Rules: | The rating and justification of the sub-criteria shown above should be used to inform the rating of the parent criterion.
The final criterion ratings should be based on the analyst's assessment of the sub-criteria ratings, rather than a strict average or formula.
Justification for the criteria rating should clearly identify what was met and not met, including references to the sub-criteria.
| Sub-criteria |  | Criteria
| Met | Green | Met | Green
| Substantially Met | LT Green | Substantially Met | Green
| Partially Met | Yellow | Partially Met | Yellow
| Minimally Met | LT Red | Minimally Met | Red
| Not Met | Red | Not Met | Red
| Not Applicable | Grey | Not Applicable | Grey
| Not Yet Rated | White | Not Yet Rated | White