RPP-27195

| CH2M HILL Hanford Group, Inc. READINESS ASSESSMENT | Manual Document Page Issue Date Effective Date | Projects TFC-PRJ-PM-C-09, REV B-6 1 of 46 January 24, 2007 January 24, 2007 |
| --- | --- | --- |

Ownership Matrix

TABLE OF CONTENTS

1.0	PURPOSE AND SCOPE	2

2.0	IMPLEMENTATION	2

3.0	RESPONSIBILITIES	2

3.1	Review Team Leader	2

3.2	Review Team Members	2

4.0	PROCEDURE	3

4.1	Readiness Assessment Plan of Action (POA) Development	4

4.2	Readiness Assessment Implementation Plan Development	6

4.3	Readiness Assessment Performance	8

4.4	Readiness Assessment Final Report	10

4.5	Readiness to Proceed Memorandum	11

4.6	DOE Readiness Assessment	12

4.7	DOE Readiness Assessment Final Report	12

4.8	Closure of Pre-Start Open Items	13

4.9	Request for Approval to Startup/Restart	13

5.0	DEFINITIONS	14

6.0	RECORDS	15

7.0	SOURCES	15

7.1	Requirements	15

7.2	References	15

TABLE OF FIGURES

Figure 1.  Readiness Assessment Flowchart.	17

TABLE OF ATTACHMENTS

ATTACHMENT A - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT POA CONTENT GUIDE	18

ATTACHMENT B - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT POA FORMAT	25

ATTACHMENT C - LEVEL 3 READINESS ASSESSMENT POA FORMAT	29

ATTACHMENT D - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT IMPLEMENTATION PLAN	36

ATTACHMENT E - PRE-START/POST-START ITEM EVALUATION CRITERIA	40

ATTACHMENT F - EVALUATION AND TRACKING OF OPEN ITEMS	43

ATTACHMENT G - READINESS ASSESSMENT FINAL REPORT FORMAT	44

# PURPOSE AND SCOPE

(7.1.2)

This procedure describes the prerequisites, responsibilities, requirements, and actions required in performing a level 1 (most complex), level 2, or level 3 (least complex) readiness assessment (RA).  An RA is performed to confirm a nuclear facility/task/activity “state of readiness” for startup or restart when an operational readiness review (ORR) is not required.  This procedure provides for a documented independent assessment and confirmation of readiness in compliance with Department of Energy (DOE) Order 425.1C, “Startup and Restart of Nuclear Facilities.”  (7.1.1.b)

Level 1, 2, and 3 RAs use a graded approach to the breadth and depth of the assessment review.  Level 1 RAs may be as complex as an ORR, whereas a level 3 RA might only consist of an Operational Readiness Checklist.  (7.1.1.c)

# IMPLEMENTATION

This procedure is effective on the date shown above.

# RESPONSIBILITIES

## Review Team Leader

The review team leader is the senior individual with the necessary qualifications for managing and conducting the RA.  In addition to participating in the RA, the review team leader is responsible for overseeing the RA process, which includes:

Defining RA team membership, including selection and qualifications

Preparing and approving the RA implementation plan

Planning, coordinating, and conducting the RA

Preparing and approving the RA final report

Estimating the level of effort and schedule requirements

Establishing RA objectives and milestones

Compiling or acquiring access to all necessary background information (e.g., description of process equipment and control measures), and

Interfacing the team with Tank Farm Contractor (TFC) management.

## Review Team Members

Review team members examine the aspects of the task/activity under review and provide assurance to themselves, TFC management, and the DOE that the equipment, procedures, and personnel associated with the task/activity are ready for startup/restart and safe operation.

Review team members conduct a broad range of tasks, which typically include, but not limited to:

Assisting the review team leader and senior members in preparation of the implementation plan

Developing acceptance criteria/performance objectives and related lines of inquiry for each assessment objective

Reviewing “as-built” drawings and other applicable procedures and documents

Compiling supporting documentation

Providing a determination that the activity complies with applicable environmental requirements and federal and state laws and regulations

Conducting the RA in accordance with criteria/performance objectives as assigned in the RA implementation plan or by the RA team leader while ensuring the principles and functions of Integrated Safety Management System are addressed

Concurring with the determination of operational readiness and the conclusions presented in the RA final report

Submitting completed certification documentation for review and approval

Assisting the team leader in preparation of the RA final report.

# PROCEDURE

Personnel are responsible for familiarizing themselves with this procedure before use.  Before performing any portion of this procedure, contact the Operational Readiness group.

NOTE:  Refer to Figure 1 Readiness Assessment Flowchart.

The startup notification report identifies the approved level (1, 2, or 3) of RA required for a task/activity startup/restart.   (7.1.1.b)

The three levels of RAs and their authorization authority are defined as follows:  (7.1.1.d)

Level 1 RA.  TFC RA followed by a DOE RA, with DOE as the authorizing authority.

Level 2 RA.  TFC RA with TFC as the authorizing authority; may have DOE as the authorizing authority when requested by DOE, and DOE oversight involving either:

Formal, focused oversight and evaluation of the TFC RA, or

Routine oversight of the TFC RA at the program manager and/or facility representative level.

Level 3 RA. TFC RA with TFC senior management as the authorizing authority.  DOE provides oversight of the TFC RA at the program manager and/or facility representative level.

## Readiness Assessment Plan of Action (POA) Development

| Director responsible for the activity | 1. | Develop the RA POA four to six months before the planned RA. (7.1.1.b) a. Develop the content for a level 1 or level 2 RA POA in accordance with Attachment A. NOTE: Aid to identifying the core requirements is found in Attachment A, Figure A-1. The format to be used for a level 1 or level 2 RA POA is located in Attachment B. b. Develop the content for a level 3 RA POA in accordance with Attachment C. c. Ensure that the POA contains the following elements, as a minimum: (7.1.1.b) Identification of the breadth of the assessment by determination of the applicable core requirements for startup/restart (7.1.1.e) Designation of the review team leader Identification of prerequisites that must be completed before initiating an RA. d. Tailor the POA to the complexity level of the required RA. NOTE: For a level 3 RA, the POA will also serve as the implementation plan. |
| --- | --- | --- |
|  | 2. | Define the prerequisites for readiness by performing the following: a. Address each applicable core requirement. (7.1.1.e) b. Identify activities that must be completed to meet the core requirements prior to initiating the RA. c. Identify and review any additional prerequisites that may be established by management or DOE. (7.1.1.b) NOTE: The core requirements and guidance on the graded approach can be found on the Operational Readiness web page. |
|  | 3. | Develop the prerequisites as specific action statements in the POA that identify what must be completed before readiness is declared. NOTE: Prerequisite statements provide for measurable evidence that the prerequisite(s) have been met. |
|  | 4. | Verify the appropriate startup/restart contractor authorization authority is identified in the POA as indicated in the startup notification report. (7.1.1.d) |
|  | 5. | Select the review team leader for the RA and name in the POA. (7.1.1.b) NOTE: Reference DOE-STD-3006-2000, Section 5.1.5.1, for guidance on selecting the review team leader. |
|  | 6. | Submit the POA to the Manager, Operational Readiness, for review. |
| Manager, Operational Readiness | 7. | Review the POA and, if necessary, provide comments to the Director responsible for the activity. |
| Director responsible for the activity | 8. | Resolve comments, as required, and submit the POA to the contractor authorization authority. |
| Contractor Authorization Authority | 9. | Approve the POA. (7.1.1.b) |
|  | 10 | For a level 1 or level 2 RA, submit the POA to DOE for review and approval. (7.1.1.b) |

|  | 11. | For a level 3 RA, submit the POA to DOE for review. |
| --- | --- | --- |
|  | 12. | When approved, provide a copy of the POA to the Manager, Operational Readiness and to the Director responsible for the activity. |
| Manager, Operational Readiness | 13. | Provide a copy of the POA to the review team leader. |

## Readiness Assessment Implementation Plan Development

NOTE:  A separate implementation plan is NOT required for a level 3 RA.  In this case, the POA will suffice to define the scope and depth of the RA.

| Review Team Leader | 1. | Select review team members using the following criteria: Technical knowledge of the area assigned for evaluation, including experience working in the technical area Knowledge of performance-based assessment processes and methods Knowledge of activity or facility-specific information Independence in that no team member may review his or her own work or who are assigned direct line management responsibility for the work being reviewed. NOTE: Reference DOE-STD-3006-2000, Sections 5.1.5.1 and 5.1.5.2, for guidance on selecting review team members. |
| --- | --- | --- |
|  | 2. | Determine the qualification and experience needed for team members based on technical aspects and complexity of the task/activity being reviewed. |
|  | 3. | Assemble team far enough in advance of the commencement of the RA to review applicable data and ensure required training is completed. |
|  | 4. | Create a team member roster, including qualification documentation for each member, for inclusion in the RA final report. |
|  | 5. | Assign specific tasks to team members based on the individual’s knowledge of the particular system, process, safety documentation, or facility as well as the review process. |
| Review Team Leader and Review Team Members | 6. | For a level 1 or level 2 RA, develop the implementation plan based on the breadth of the assessment contained in the POA in accordance with the criteria contained in Attachment D. NOTE: A graded approach is used to determine the level of detail (the depth of planning required for the RA). The combination of breadth and depth forms the envelope or scope within which the RA is conducted. The implementation plan should specify this scope including breadth and depth. NOTE: Guidance on the graded approach can be found on the Operational Readiness web page. |
|  | 7. | Develop criteria and review approach documents based on the POA that will provide the means through which the graded approach is applied to the scope of the RA as follows: a. Begin each criteria and review approach document with a core requirement or some portion of the core requirement. NOTE: This will ensure that all core requirements are addressed by criteria regardless of the approach used in developing the criteria. b. Identify the specific criteria that address the core requirement or portion of a core requirement. NOTE: Each criterion is a statement of the specific action(s) or attributes the reviewer(s) use to make a judgment as to the readiness of the site or task/activity to operate in this specific area. c. Identify the review approach. NOTE: This section describes the documents to be reviewed, the personnel to be interviewed, and the shift evolutions (including tours and walk downs) to be observed to determine if the criteria have been met. NOTE: Reference DOE-STD-3006-2000, Section 5.4.5 and Appendix 4, for example, criteria, and review approach documents. |
| Review Team Leader | 8. | Approve the implementation plan. |
|  | 9. | Provide a copy of the implementation plan to the contractor authorization authority and the Manager, Operational Readiness. |

## Readiness Assessment Performance

| Director responsible for the activity | 1. | Provide the “declaration of readiness” memorandum to the contractor authorization authority after the following have been completed: (7.1.1.a) Startup management self-assessment, completed in accordance with TFC-PRJ-PM-C-07 Prerequisites in the RA POA with evidence of completion. (7.1.1.a) NOTE: The Director responsible for the activityfacility manager may include in the “declaration of readiness” memorandum a “manageable list” of open pre-start and post-start items. Acceptability of the “manageable list” of open items should be discussed with the Manager, Operational Readiness. |
| --- | --- | --- |
| Contractor Authorization Authority | 2. | Approve the declaration of readiness memorandum. |
|  | 3. | Provide a copy of the declaration of readiness memorandum to the review team leader and direct the review team leader to commence the RA. |
|  | 4. | Inform the DOE of the commencement of the RA. |
| Review Team Leader | 5. | Conduct the RA in accordance with: Approved implementation plan (level 1 and 2), as applicable, or Approved POA (level 3). |
| RA Team/Review Team Leader | 6. | If the team (with concurrence of the review team leader) or the review team leader decides the task/activity is not ready during the RA, stop the RA. |
| Review Team Leader | 7. | Provide a letter to the contractor authorization authority detailing the reason(s) for stopping the RA. NOTE: In this case, no final report is required but the Director responsible for the activity should generate a Problem Evaluation Request (PER) in accordance with TFC-ESHQ-Q_C-C-01. |
| Review Team Members | 8. | Perform assigned tasks, which typically include: Conducting the RA in accordance with the review criteria/ performance objectives that address the principles and functions of Integrated Safety Management System Concurring with the readiness status and the conclusions presented in the final report Submitting completed issue documentation for review and approval Assisting the review team leader in the preparation of the final report. |
| Review Team Leader and Director responsible for the activity | 9. | Conduct a daily debrief to review issues (potential findings and observations) identified during the RA, as required. |
| Director responsible for the activity | 10. | Provide resources required to support the RA activities. |
|  | 11. | Notify the contractor authorization authority of any emerging item following the declaration of readiness and document determination as to its impact on readiness. |
| Review Team Members | 12. | Document the assessment on the Assessment Form and forward the form to the review team leader. NOTE: The Assessment Form, Deficiency Form, and Finding Resolution Form (also called Forms 1, 2, and 3, respectively) may be obtained from the Manager, Operational Readiness. |
|  | 13. | Review all issues (findings and observations) and evaluate readiness of the activity/task using the criteria stated in the implementation plan. NOTE: Use the criteria and review approach documents when reviewing documents, observing operations, observing drills, conducting interviews, etc., as part of the review. |
|  | 14. | Document issues (findings and observations) upon completion of the assessment in accordance with the implementation plan using the Deficiency Form. |
|  | 15. | Sign and forward the Deficiency Form to the review team leader. |
| Review Team Leader and Review Team Members | 16. | Categorize findings in accordance with Attachment E, Figure E-1, as either pre-start or post-start. NOTE: Dissenting opinions may be included as an attachment to the final report. |
| Review Team Leader | 17. | Review the finding categorization with the Director responsible for the activity. |
|  | 18. | Compile findings and observations after the RA is completed. |
|  | 19. | Verify that findings and observations have been brought to the attention of the Director responsible for the activity for corrective action(s). |
| Director responsible for the activity | 20. | Monitor and track results of the RA ensuring that issues identified by the review team and any emerging items (e.g., equipment malfunction) identified are entered as open items in accordance with Attachment F. |

## Readiness Assessment Final Report

| Review Team Leader and Review Team Members | 1. | Prepare the RA final report. NOTE: Refer to Attachment G for guidance on content and format. NOTE: The final report should be clear and easy to understand and should include only facts that directly relate to assessment observations and results. Additionally, it should include sufficient information to enable the assessed organization to check the report for accuracy and to develop and implement appropriate improvement plans. a. For a level 1 or level 2 RA, follow the format in Attachment G. b. For a level 3 RA, prepare the final report in the form of an executive summary. |
| --- | --- | --- |
| Review Team Leader | 2. | Ensure the final report makes a conclusion as to whether startup or restart can proceed safety. |
|  | 3. | Approve the final report and submit to the contractor authorization authority. |
|  | 4. | Provide a copy of the approved final report to the Director responsible for the activity. |
| Director responsible for the activity | 5. | Coordinate review of the final report and determination of the corrective action plans. a. If no corrective actions are required, go to Section 4.5. |
|  | 6. | For each finding perform the following: a. Complete a Finding Resolution Form in accordance with Attachment F, and generate a PER in accordance with TFC-ESHQ-Q_C-C-01. b. Enter on the open items list. |
|  | 7. | Track and close pre-start findings. |
|  | 8. | Coordinate development of corrective action plan(s) for post-start findings in accordance with Attachment F. |
|  | 9. | Examine issues from the RA (including those closed during the assessment) to determine programmatic issues and causes. |
|  | 10. | Monitor and track progress of open items, while bringing as many as possible to closure. |

## Readiness to Proceed Memorandum

| Director responsible for the activity | 1. | Generate a “readiness to proceed” memorandum with the following attachments: RA final report Open items list (from the startup management self-assessment and the contractor readiness assessment) Corrective action plan(s). NOTE: The Director responsible for the activity may generate a “readiness to proceed” memorandum with a “manageable list” of open pre-start and post-start items. Acceptability of the “manageable list” of open items should be discussed with the Manager, Operational Readiness. |
| --- | --- | --- |
|  | 2. | Submit the “readiness to proceed” memorandum to the contractor authorization authority. |

| Contractor Authorization Authority | 3. | Approve the “readiness to proceed” memorandum certifying that all prerequisites in the POA have been met. (7.1.1.a) |
| --- | --- | --- |
|  | 4. | If a DOE RA is to be performed, submit the “readiness to proceed” memorandum (along with all attachments) to DOE. |
|  | 5. | If no DOE RA is to be performed, go to Section 4.8. |

## DOE Readiness Assessment

| Director responsible for the activity | 1. | If the startup notification report requires a DOE RA, provide resources required to support DOE RA team activities. |
| --- | --- | --- |
|  | 2. | Monitor, track, and close open items resulting from the DOE RA. |
|  | 3. | Ensure issues identified by the review team are entered as open items in accordance with Attachment F. |
|  | 4. | Continue to bring as many open items as possible to closure. |

## DOE Readiness Assessment Final Report

| Director responsible for the activity | 1. | If an RA was performed, coordinate review of the DOE RA final report and determination of corrective action plans. |
| --- | --- | --- |
|  | 2. | If no corrective actions are required, go to Section 4.8. |
|  | 3. | For each finding perform the following. a. Complete a Finding Resolution Form in accordance with Attachment F, and generate a PER in accordance with TFC-ESHQ-Q_C-C-01. b. Enter on the open items list. |
|  | 4. | Track and close DOE pre-start findings. |
|  | 5. | Coordinate development of corrective action plan(s) for post-start findings in accordance with Attachment F. |
|  | 6. | Monitor and track progress of open items continuing to bring as many as possible to closure. |
|  | 7. | Examine issues from the DOE RA (including those closed during the assessment) to determine programmatic issues and causes. |

|  | 8. | Submit corrective action plan(s) to the contractor authorization authority for approval. |
| --- | --- | --- |
| Contractor Authorization Authority | 9. | Review and approve the corrective action plan(s). |
|  | 10. | Submit the corrective action plan(s) to the DOE for approval. |

## Closure of Pre-Start Open Items

| Director responsible for the activity | 1. | Following completion of the last RA activity, coordinate review of the following for potential impact on, and possible inclusion in, the open items list: Open applicable non-conformance report(s) Open PERs Open Work Management System items. |
| --- | --- | --- |
|  | 2. | Verify closure of pre-start items. |
|  | 3. | Obtain the RA review team leader “verified by” signature on Finding Resolution Form for each closed pre-start finding. |
|  | 4. | Assemble verification documentation for all pre-start open items and insert in the readiness review certification package. NOTE: The readiness review certification package contains the affidavit packages, along with the sufficient objective evidence, as needed, that supports operational readiness. |
|  | 5. | Develop lessons learned from the RA and provide an electronic copy to the Manager, Operational Readiness. NOTE: Lessons learned will be from both RA final reports and the startup management self-assessment. |

## Request for Approval to Startup/Restart

| Director responsible for the activity | 1. | Verify closure of all pre-start items. |
| --- | --- | --- |
|  | 2. | Verify that a PER has been generated for each open post-start item. |
|  | 3. | Submit a letter to the contractor authorization authority requesting approval to startup/restart. NOTE: Attachments to the letter shall include: Evidence of closure for pre-start findings Corrective action plan(s) and schedules for post-start findings |
| Contractor Authorization Authority | 4. | Review and approve startup/restart. (7.1.1.d) |
|  | 5. | Notify Director responsible for the activity and direct the startup/restart of the task/activity. |
|  | 6. | Provide notification to DOE that startup/restart is approved. |
|  | 7. | If DOE is the authorization authority, submit a letter to DOE requesting approval to startup/restart. (7.1.1.d) NOTE: Attachments to the letter shall include: Evidence of closure for pre-start findings Corrective action plan(s) and schedules for post-start findings |
|  | 8. | When DOE approval is given, notify the Director responsible for the activity and direct startup/restart of the task/activity. (7.1.1.d) |

# DEFINITIONS

Declaration of readiness.  Formal communication from the Director responsible for the activity to the Contractor Authorization Authority stating that the startup management self-assessment and the prerequisites in the POA have been completed.  The declaration is a prerequisite to authorizing the start of the contractor Operational Readiness Review or Readiness Assessment.

Concern.  A determination of a programmatic breakdown or widespread problem supported by one or more findings or observations.

Finding.  An individual item that does not meet a committed requirement (e.g., contract, regulation, authorization basis document, contractor commitment, and standards/requirements identification documents).

Issue.  An item under discussion or in dispute where the final conclusion or decision will constitute it being classified as a finding, an observation, a concern, or it being dismissed.

Observation.  A condition or practice that does not provide or promote effective protection of the health and safety of the public, or DOE workers, or the environment, but is not directly linked to compliance.

Readiness to Proceed Memorandum.  Formal communication from the contractor to DOE stating that the task/activity has been brought to a state of readiness to start operations.  The memorandum is a prerequisite to the DOE ORR/RA, if required.  It is issued after the contractor Operational Readiness Review or Readiness Assessment is completed certifying that all prerequisites in the POA have been completed.  It is developed by the Director responsible for the activity for approval by the Contractor Authorization Authority before sending to DOE, declaring that the task/activity has been brought to a state of readiness to start operations and ready for the DOE ORR/RA, if required.

# RECORDS

The following records are generated during the performance of this procedure:

Readiness Assessment POA

Readiness Assessment final report

Readiness to Proceed memorandum with attachments

Startup/Restart Request letter with attachments.

The Operational Readiness group is responsible for record retention and retirement in accordance with TFC-BSM-IRM_DC-C-02.

# SOURCES

## Requirements

#### DOE O 425.1C, “Startup and Restart of Nuclear Facilities,” Attachment 1, Contractor Requirements Document.  (S/RID)

##### Paragraph 2.b.(7).

##### Paragraph 2.c.(1).

##### Paragraph 2.c.(2).

##### Paragraph 2.c.(3).

##### Paragraph 2.d.

#### RPP-MP-003, “Integrated Environment, Safety, and Health Management System Description for the Tank Farm Contractor.”

## References

#### DOE-HDBK-3012-96, “Guide to Good Practices for Operational Readiness Reviews (ORR) Team Leader’s Guide.”

#### DOE ORP M 425.1, “Startup and Restart of Tank Farm Contractor Nuclear Facilities.”

#### DOE-STD-3006-2000, “Planning and Conduct of Operational Readiness Reviews.”

#### TFC-ESHQ-Q_C-C-01, “Problem Evaluation Request.”

#### TFC-BSM-IRM_DC-C-02, “Records Management.”

#### Operational Readiness web page.

Figure 1.  Readiness Assessment Flowchart.

ATTACHMENT A - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT POA CONTENT GUIDE

The POA sets the stage for a structured and independent verification of task/activity readiness to startup/restart.  It is the document by which management defines what will be evaluated during the RA.  It provides personnel with vital initial information regarding the planned readiness process.  The POA includes the following information as a minimum:  (7.1.1.b)

- Designated review team leader.

- Description of the breadth of the assessment.  The Core Requirements of DOE Order 425.1C that will be assessed; for those that will not be assessed, the POA provides the justification for not addressing them as part of the assessment.  The purpose of the Core Requirements is to assess the readiness of the facility personnel, programs, and equipment to conduct work safely (7.1.1.e)

- Prerequisites that must be completed before initiating the RA.  Prerequisites, when completed, are expected to bring the activity into a state of readiness.  Therefore, prerequisites must address the entire scope of the RA.

The POA addresses the minimum set of core requirements that must be addressed when developing the breadth. When determining the breadth of the POA the startup/restart description and operational acceptance checklist should be referenced as they describe the work scope and the differences between the subject activity and previous activities. During the RA the review team, if appropriate, may expand the breadth.

The POA is developed using a graded approach to the tenets of the requirements specified in DOE Order 425.1C.  The RA is tailored to the degree that is needed.  The requirements depend on knowledgeable people identifying relevant topics based on their experience, the facility characteristics, operating environment, the operating and support organizations capability, and the risk associated with the proposed startup or restart.  It must be consistent with the circumstances, changes, duration, and confidence since the operations were last conducted.  (7.1.1.c)

For use of the graded approach and a list of the Core Requirements, reference the Operational Readiness web page.

The POA is drafted by the Director responsible for the activity and approved by the Contractor Authorization Authority.  (7.1.1.b)

Further POA details can be found in DOE-STD-3006-2000, Sections 5.9.1, 5.10, Appendixes 1 and 2.

Two important actions in the development of the POA is the definition of the breadth of the assessment and the creation of the list of criteria that are to be verified to support readiness.  Identification of the criteria is accomplished by an evaluation of the activity/task to determine what is different from the operations on-going in which the activity/task is to be started and operated.  For example, if the operations personnel for the activity/task were newly assigned, trained and qualified, then the operators would be evaluated during the RA.  If the activity/task is in an operating facility in which all support programs and systems already function and different functions are not required for the activity/ task, the support programs and systems would NOT be included in the POA for the RA.

ATTACHMENT A – Level 1 AND Level 2 Readiness Assessment POA CONTENT Guide (cont.)

Those organizations or programs that are identified as providing a product or service required for startup/restart may be excluded from the assessment because their function has not changed as a result of the startup/restart.  However, those programs/organizations must be prepared to demonstrate that their function has been implemented in compliance with applicable management requirements and contractual flow-down requirements.

ATTACHMENT A – Level 1 AND Level 2 Readiness Assessment POA CONTENT Guide (cont.)

Figure A-1.  Identification of the Core Requirements to be Included in the POA.

Activity/Task: ______________________________________________________________

The two key elements of the POA are the criteria or objectives to be reviewed and the prerequisites to ensure readiness for operation.  The following process provides a method to identify the minimum criteria or objectives that should be included in the POA.  The depth of each criteria or objective (Implementation Plan) as well as the prerequisites will logically follow once the breadth has been defined.

| STEP ONE: Identification of the Core Requirements to be Included in the POA. |
| --- |
| Consider the following questions in regard to the activity/task for which the POA is being developed: | If “Yes” the Core Requirement(s) listed should be considered for inclusion in the POA. |
| Will new operating or support personnel be required for the activity/task? Personnel must be identified by job description or position (e.g., nuclear chemical operator, electrician, etc.). The level of training and qualification should be understood. The Core Requirements must evaluate that the training program and the execution of that program are adequate to assure that the new personnel can safely conduct operations. The review includes programs, records, and activity/task knowledge. Personnel are considered new because they have not performed the operation before or are new to the job position. | Yes [ ] No [ ] 1, 2, 3, 4, 5, 6 |
| Will new management personnel be assigned to the activity/task? Management personnel should be identified by job description or position (e.g., Shift Manager, Operations Manager, etc.). The management selection and training process may not be new, therefore not require evaluation. The breadth of the assessment may be to determine that the new managers meet the selection criteria and understand their individual responsibilities. | Yes [ ] No [ ] 1, 2, 3, 4, 6 |
| Will existing operations or support personnel require retraining or re-qualification for the activity/task? Personnel should be identified by job description or position. The changes in existing qualification requirements or the new qualification requirements that are required should be identified. The new records and level of knowledge of the activity/task should be the extent of the depth of the core objectives. | Yes [ ] No [ ] 1, 2, 3, 4, 5, 6 |
| Will safety class SSCs require modification to support the activity/task? Safety-class SSCs that have been modified, and the extent of the modifications should be described. The individual Core Requirements should be evaluated to the degree necessary to insure the affects of the modifications have been reflected in the safety documentation, maintenance and operational procedures, and the training and qualification requirements. The result of question 11 will also have a bearing on the depth of the individual Core Requirements. | Yes [ ] No [ ] 5, 7, 8, 9, 10, 12 |

ATTACHMENT A – Level 1 AND Level 2 Readiness Assessment POA CONTENT Guide (cont.)

Figure A-1. Identification of the Core Requirements to be Included in the POA.  (cont.)

| STEP ONE: Identification of the Core Requirements to be Included in the POA. |
| --- |
| Consider the following questions in regard to the activity/task for which the POA is being developed: | If “Yes” the Core Requirement(s) listed should be considered for inclusion in the POA. |
| Will safety-significant SSCs require modification to support the activity/task? Safety-significant SSCs that have been modified, and the extent of the modifications should be described. The individual Core Requirements should be evaluated to the degree necessary to insure the affects of the modifications have been reflected in the safety documentation, maintenance and operational procedures, and the training and qualification requirements. The result of question 11 will also have a bearing on the depth of the individual Core Requirements. | Yes [ ] No [ ] 5, 7, 8, 9, 10, 12 |
| Will new processing systems or components be installed to support the activity/task? The new systems and components should be listed. Configuration management of the systems and components must be evaluated, including the technical baseline and change control processes. Post installation testing will be evaluated. The depth discussion will indicate the impact of the changes on procedures, test documentation, training, and qualifications. | Yes [ ] No [ ] 5, 7, 8, 9, 10, 12 |
| Will existing processing systems or components be modified or restarted following extended shutdowns to support the activity/task? | Yes [ ] No [ ] 5, 7, 8, 9, 10, 12 |
| Will site support programs require modifications to meet the needs of the activity/task? See #9 Below | Yes [ ] No [ ] 1, 2, 3, 4 |
| Will (any) site support programs have a significant interface or unusual involvement with the activity/task? Both Questions 8 and 9 require the same consideration to define the breadth and depth of evaluation. The support programs that require evaluation will be identified. The degree of the evaluation will then be described. For example, it may not be necessary to evaluate the training and qualification programs for ongoing support programs, only the availability and capability of personnel, and their understanding of their role in supporting the activity/task. If a support program were to require significant change, more depth would be specified than if it were only an extension of an existing program. | Yes [ ] No [ ] 2, 3, 4, 5, 6 |

ATTACHMENT A – Level 1 AND Level 2 Readiness Assessment POA CONTENT Guide (cont.)

Figure A-1. Identification of the Core Requirements to be Included in the POA.  (cont.)

| STEP ONE: Identification of the Core Requirements to be Included in the POA. |
| --- |
| Consider the following questions in regard to the activity/task for which the POA is being developed: | If “Yes” the Core Requirement(s) listed should be considered for inclusion in the POA. |
| Will new or modified procedures be required to carry out the startup/restart of the activity/task? List the affected procedures. The individual Core Requirements will evaluate, as necessary, adequate procedure changes were met, properly managed, and that the personnel have been trained on the latest versions. This question is closely related to Questions 4, 5, 6, and 7. | Yes [ ] No [ ] 9, 10, 13 |
| Will facility safety documentation require changes to accommodate the activity/task? (e.g., SAR, TSR, BIO, etc.) Did the USQD process evaluation determine that no changes to the safety documentation exists? Identify the safety documentation related to the activity/task and the changes that are required. The Core Requirements will as necessary, insure the changes to the safety documentation were adequately incorporated in all derivative, flow down documents and procedures. | Yes [ ] No [ ] 7, 9, 10 |
| Will the activity/task require changes to the Emergency Preparedness Program (e.g., add new scenarios)? Describe the changes to the Emergency Preparedness Program. The breadth of the evaluation will be as necessary to review the adequacy of the program following changes. The information associated with Questions 1 and 10 will affect the depth of this Core Requirement. | Yes [ ] No [ ] 11 |
| Will the startup test program be required to verify readiness to startup/restart or will additional oversight be used to validate procedure/personnel adequacy due to inability to fully demonstrate performance? Describe the details of the processing. The presumption is that it will be done in accordance with a startup plan. The startup plan, evaluation criteria, methods for removing controls, evaluations and qualifications, and recording of results should be reviewed for adequacy as part of the readiness review. | Yes [ ] No [ ] 12 |

ATTACHMENT A – Level 1 AND Level 2 Readiness Assessment POA CONTENT Guide (cont.)

Figure A-1. Identification of the Core Requirements to be Included in the POA.  (cont.)

| STEP ONE: Identification of the Core Requirements to be Included in the POA. |
| --- |
| Consider the following questions in regard to the activity/task for which the POA is being developed: | If “Yes” the Core Requirement(s) listed should be considered for inclusion in the POA. |
| Will changes to the Conduct of Operations implementation matrix or procedures be required to accommodate the activity/task? Describe changes. New chapters may be required. New control rooms may be brought into operation. The description of the project and the changes required should define the depth of the evaluation of Conduct of Operations. The current status of Conduct of Operations compliance should also be considered (e.g., recent reviews indicate lax step-by-step procedure compliance). The operational formality demonstrated by operations personnel will be evaluated based on Questions 1, 3, and 10. | Yes [ ] No [ ] 13 |
| Does the activity/task require a specific evaluation of the issues management program or corrective action status? If the question was answered “Yes” it will provide the basis for the depth of the core objective. In general, all open issues within the facility should be evaluated for proper closure or technical basis to justify their remaining open (i.e., pre/post screening). | Yes [ ] No [ ] 15 |
| Does the activity/task require a specific evaluation of formal contract agreements, caused by changes in contractor agreements with the DOE, state, or local government. If the question was answered “Yes” it will provide the basis for the depth of the core objective. The requirements have been implemented in the facility or compensatory measures are in place and formally agreed to during the period of implementation. | Yes [ ] No [ ] 14 |

ATTACHMENT A – Level 1 AND Level 2 Readiness Assessment POA CONTENT Guide (cont.)

Figure A-1. Identification of the Core Requirements to be Included in the POA.  (cont.)

STEP TWO: Description Or Identification Of Prerequisites to the Readiness Review.

Upon completion of STEP ONE, the actions and conditions necessary to satisfactorily complete the RA should be clear.  The prerequisites are identified as action steps which, when satisfied, will ensure readiness.  For example, STEP ONE identified the personnel required, the procedures requiring change, the systems being installed and tested, etc.  This information defines specifically what must be completed to achieve readiness to startup/restart.  In addition, the detailed description of the activity/task should lead to an understanding of what actions must be completed in order to bring the activity/task to a state of readiness to startup/restart.

Action statements that describe these requirements should be developed and included as prerequisites in the POA.  These prerequisites must address the entire scope of the review.  Prerequisites must address each applicable Core Requirement.  It is not acceptable to have one prerequisite stating that all Core Requirements have been met.  Some Core Requirements will require several prerequisites to ensure satisfactory completion.  An example is “Core Requirement 3,” where it would be prudent to have several prerequisites for operations and each of the support organizations.  This method will facilitate better organization of evidence and allow for easier tracking of prerequisite completion.

ATTACHMENT B - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT POA FORMAT

Cover Page

- CH2M HILL

- PLAN-OF-ACTION

- Activity/Task Identification (PROJECT W-XXX)

- Project Name

- Level 1 or level 2 Readiness Assessment

- PLAN OF ACTION Number

- Revision

Page Two

- Project Name

- Reviews and Concurrence

- Approval

Page Three

- Project Name

- Table of Contents

1.0	Name of the Facility (or Task or Activity)

The name must be specific about what will be evaluated and started.  If a single process within a building will be restarted, the facility name would be the process name; if the process encompasses several buildings and an area, the name would be the encompassing process name.

2.0	Description of Facility

This includes buildings, systems, and processes included in the startup/restart of activities.  The description may be instrumental in defining the RA scope; therefore, ensure a complete and accurate description.  For example, if most support functions and procedures are outside the boundary of the facility under review, the RA would focus on interfaces within existing programs.  A facility one-line simple drawing, if available, should be included.

Use the Startup Notification Report (SNR) and the Startup/Restart Description (SRD) for this information.

Evaluation of Activities – Location and a detailed description of the activity/task.

ATTACHMENT B - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT POA FORMAT (cont.)

3.0	Identification of the Responsible Contractor

The contractor that will certify the readiness of the facility to operate.

4.0	Startup/Restart Discussion

Discuss the following: hazard categorization of the facility once restarted and the basis for determination (criticality, explosive, chemical, environmental, etc.), cause for shutdown, last day of operation, duration of shutdown, repairs accomplished during shutdown period, modifications accomplished during shutdown period and the affect on the approved authorization basis, and any anticipated process changes after startup or restart.

Use the SRD for this information.

4.1	Hazard Category

Use the SRD for this information.

4.2	Cause for Shutdown

Use the  SRD for this information.

4.3	Duration of Shutdown

Use the  SRD for this information.

4.4	Repairs and Modifications during the Shutdown

Use the SRD for this information.

4.5	Process Changes

Use the  SRD for this information.

ATTACHMENT B - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT POA FORMAT (cont.)

5.0	Proposed Breadth of Readiness Assessment

(7.1.1.c, 7.1.1.e)

This is a key section because the breadth identifies the top tier Core Requirements for consideration during the RA activities.  The breadth starts with the minimum Core Requirements which are the 15 Core Requirements of DOE Order 425.1C, the physical scope in the facility description, and the addition of adequate implementation of the Integrated Safety Management System (ISMS).  Only those Core Requirements deemed applicable need to be addressed.

The discussion of the breadth of the RA in the POA supports the development in the RA Implementation Plan of the depth of each aspect of the RA.  In support of this function of the POA, and to ensure maximum understanding regarding the intention of the restart authority as to what should be reviewed, care and attention to detail are important in the development of the breadth section of the POA.  The breadth must start with a clear discussion of the physical scope of the RA.  A clear definition of the structures, systems, and components, as well as the individual processes or activities that are within the scope of the RA should be provided.  Clarity is best achieved by discussing each Core Requirement individually.  The discussion should clearly describe the detail or depth to which each is to be reviewed.

6.0	Core Requirements Excluded From Readiness Assessment

Justification will be provided here if it is determined that a particular Core Requirement will not be reviewed as part of the RA.  A discussion follows each Core Requirement or group of Core Requirements to provide justification to exclude them from the RA.

For a level 1 RA, the level and depth of discussion for Core Requirements excluded from the RA should be equal to that required by an Operational Readiness Review.

For a level 2 RA, at a minimum, a brief discussion should follow the Core Requirement or group of Core Requirements to justify the decision to exclude them from the RA.

7.0	READINESS ASSESSMENT PREREQUISITES

(7.1.1.b, 7.1.1.e)

Defining the prerequisite conditions to be met by the facility management before the start of the RA is an important element of the readiness review.  The prerequisites address each Core Requirement or checklist functional area of the breadth of the review.  The prerequisites are described in terms of specific measurable items.

The applicable core requirements address the following prerequisites, as applicable:

- Are the safety authorization bases applicable to the project approved, signed, and implemented?

- Is construction complete and has testing applicable to the project been satisfactorily completed and documented?

ATTACHMENT B - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT POA FORMAT (cont.)

- Are personnel applicable to the task/activity qualified/certified?

- Are operations procedures applicable to the project that implements the safety basis requirements written, verified, and performed?

- Are maintenance procedures applicable to the project that implement the safety basis requirements written, verified, and performed?

- Are modifications and testing completed, signed off and individuals qualified to use the modification?

- Are emergency procedures applicable to the project written, verified, and performed?

- Are alarm response procedures applicable to the project written, verified, and performed?

- Are “off-normal” operations drills applicable to the project written, verified, and performed?

- Is Conduct of Operations implemented per the matrix of applicability for this project?

8.0	Estimated Start Date and Duration

The date is for planning purposes only and should be the best estimate.  Identification of a date is NOT to infer that the RA start will be schedule driven rather than readiness driven.

9.0	PROPOSED REVIEW TEAM LEADER

(7.1.1.b)

The name of the proposed review team leader.  The review team leader will meet the requirements of DOE-STD-3006-2000, Section 5.1.5.1.

10.0	Startup/Restart Authorization Authority

(7.1.1.d)

The name of the Startup/Restart Authorization Authority.

11.0	References

Attachments

ATTACHMENT C - LEVEL 3 READINESS ASSESSMENT POA FORMAT

Cover Page

- CH2M Hill

- PLAN-OF-ACTION

- Activity/Task Identification (PROJECT W-XXX)

- Project Name

- Level 3 Readiness Assessment

- PLAN OF ACTION Number

- Revision

Page Two

- Reviews and Concurrence

- Approval

Section I.	Activity Description

Activity

A description of Activity.

- Use the Startup/Restart Description (SRD) for this information.

Facility Location

Facility Description and Categorization.

- Use the SRD for this information.

Scope

This information should be drawn from the Activity Description used for initial evaluation of the task.  The following information found in the SRD should be used:

- Repairs accomplished during the shutdown (if applicable)

- Modifications accomplished during the shutdown period

- Affect on the Authorization Basis (if applicable)

- Any process changes (if applicable)

- Complexity of the activity.

ATTACHMENT C – Level 3 Readiness Assessment POA FormAT (cont.)

Personnel

Use the SRD for this information.  Identify any changes in the following:

- Training qualifications

- Procedures

- Personnel hazards

- Operating personnel.

Equipment

Major equipment, controllers, instruments, gauges, etc.  A simple one-line drawing showing the major components and boundaries should be included.

Documents

- Procedures

- Configuration management

- Round sheets, data sheets, etc.

- Authorization Bases/Safety documents (e.g., SAR/BIO/TSR/OSR/USQD, etc.).

Proposed Review Team Leader

(7.1.1.b)

The name of the proposed review team leader.  The review team leader will meet the requirements of DOE-STD-3006-2000, Section 5.1.5.1.

Startup/Restart Authorization Authority

(7.1.1.d)

The name of the Startup/Restart Authorization Authority.

Section II.	Scope of the Readiness Assessment

(7.1.1.b)

The criteria that define the scope for this assessment are listed on the following Readiness Checklist.

ATTACHMENT C – Level 3 Readiness Assessment POA FormAT (cont.)

Figure C-1.  Readiness Checklist.

| READINESS CHECKLIST |
| --- |
| Activity/Task ID: Activity/Task Title: |
| Check “Yes” or “No”. Provide a basis for all items checked “N/A.” | Core Requirement(s) |
| [ ] Yes [ ] No [ ] N/A | Authorization Basis documents are current, approved, and properly controlled. Basis: | 7, 9, 10 |
| [ ] Yes [ ] No [ ] N/A | Change Evaluations/USQD process/USQD support facility operation. Basis: | 7, 9, 10 |
| [ ] Yes [ ] No [ ] N/A | Personnel are aware of Authorization Basis conditions of operations. Basis: | 1, 2, 3, 4, 5 |
| [ ] Yes [ ] No [ ] N/A | Procedures and work instructions are current, approved, and properly controlled. Basis: | 7, 9, 10, 13 |
| [ ] Yes [ ] No [ ] N/A | Personnel required for activity performance have completed training and qualification requirements, including familiarization with the latest revision of procedures required for activity/task performance. Basis: | 1, 2, 3, 4, 5, 6 |
| [ ] Yes [ ] No [ ] N/A | Personnel have established proficiency in the activity/task to be conducted. Basis: | 1, 2, 3, 4, 5, 6 |
| [ ] Yes [ ] No [ ] N/A | A Worksite Hazard Analysis is completed and necessary controls implemented in accordance with TFC-ESHQ-S SAF-C-02, Job Hazard Analysis. Basis: | 7, 13, 14 |

ATTACHMENT C – Level 3 Readiness Assessment POA FormAT (cont.)

Figure C-1.  Readiness Checklist (cont.)

| READINESS CHECKLIST |
| --- |
| Activity/Task ID: Activity/Task Title: |
| Check “Yes” or “No”. Provide a basis for all items checked “N/A.” | Core Requirement(s) |
| [ ] Yes [ ] No [ ] N/A | Critical lifts required for activity/task performance have been reviewed and approved by the Hoisting and Rigging Committee or designee, as required. Basis: | 7,13 |
| [ ] Yes [ ] No [ ] N/A | Required permits/plans (e.g., RWP, BWP, lifts, NOCs, etc.) are approved and implemented. Basis: | 7, 13 |
| [ ] Yes [ ] No [ ] N/A | Equipment/tooling required for activity/task performance has been identified, verified operational, and calibrated as applicable. Basis: | 1, 7, 8, 13 |
| [ ] Yes [ ] No [ ] N/A | All Work Order post-installation testing for the activity/task is complete and the work orders are complete through Operations Acceptance. Basis: | 7, 9, 10, 12, 13 |
| [ ] Yes [ ] No [ ] N/A | Maintenance records have been reviewed and a pre-start or post-start applicability determined. All pre-start maintenance work is complete through Operations Acceptance. Basis: | 8, 13, 14 |
| [ ] Yes [ ] No [ ] N/A | Affected Technical Basis Documents have been developed or revised, and the packages closed. Basis: | 7, 9, 10 |
| [ ] Yes [ ] No [ ] N/A | Equipment pre-operational testing is complete and the test results are approved. Basis | 10, 12, 13 |

ATTACHMENT C – Level 3 Readiness Assessment POA FormAT (cont.)

Figure C-1.  Readiness Checklist (cont.)

| READINESS CHECKLIST |
| --- |
| Activity/Task ID: Activity/Task Title: |
| Check “Yes” or “No”. Provide a basis for all items checked “N/A.” | Core Requirement(s) |
| [ ] Yes [ ] No [ ] N/A | All Personal Protective Equipment (PPE) required for this activity/task is available in acceptable condition and sufficient quantity to support operations. Basis: | 7, 13, 14 |
| [ ] Yes [ ] No [ ] N/A | All necessary supporting utilities and support services have reported readiness to support startup or restart of the activity by their responsible managers. Basis: | 1, 2, 8, 11 |
| [ ] Yes [ ] No [ ] N/A | System limits, process limits, or hazardous material limits have been identified and implemented in appropriate procedures, work instructions, etc., for conduct of the activity/task. Basis: | 8, 12 |
| [ ] Yes [ ] No [ ] N/A | Safeguards and security issues have been identified and addressed. Basis: | 7, 8, 9, 10 |
| [ ] Yes [ ] No [ ] N/A | Environmental permit requirements and exemptions have been reviewed and implemented to ensure compliance. Basis: | 7, 9, 10 |
| [ ] Yes [ ] No [ ] N/A | Applicable Lessons Learned have been reviewed and identified issues resolved. Basis: | 15 |
| [ ] Yes [ ] No [ ] N/A | Sufficient personnel have been assigned responsibilities to support the safe startup and operations of this facility. Basis: | 2, 11 |
| [ ] Yes [ ] No [ ] N/A | Basis: |  |

ATTACHMENT C – Level 3 Readiness Assessment POA FormAT (cont.)

Figure C-1.  Readiness Checklist (cont.)

READINESS CHECKLIST

Activity/Task ID: Activity/Task Title:

Notification, Concurrence and Approvals

The checklist criteria have been met and the activity/task is ready for operational authorization. Review Team Leader: ______________________________ Date: _______________ Name

The information provided herein is accurate and complete. I recommend approval of permission to conduct the activity/task. Director responsible for the activity: ______________________________ Date: _______________ Name

Concurrence Signature: ______________________________________ Date: _______________ If Required Name/Title Concurrence Signature: ______________________________________ Date: _______________ If Required Name/Title Concurrence Signature: ______________________________________ Date: _______________ If Required Name/Title

Operational Authorization is granted. Contractor Authorization Authority: ______________________________ Date: _______________ Name/Title

DOE Representative: ______________________________ was notified of the intent to conduct activity/task Name Contacted by: __________________________________________ Date: _______________ Name/Title

ATTACHMENT C – Level 3 Readiness Assessment POA FormAT (cont.)

Section III.	Prerequisites

(7.1.1.b)

This section lists the prerequisites that must be met.

NOTE:  These are the minimum prerequisites that are required.  Your specific activity may require more.

- The Operational Readiness Checklist has been completed and approved by the Director responsible for the activity.

- A USQD has been performed on the new task and found to NOT present an unreviewed safety question.

- The Director responsible for the activity has verified that the controlling procedure(s) is current, approved, and can be performed as written and that the operators are proficient in the use of the procedure(s).

- Required testing and calibrations are complete and test exceptions have been dispositioned.

- Open items against the facility have been dispositioned, including closure of all pre-start items.

- All pre-start work packages are completed through Operations Acceptance.

- All specified training and qualification activities are complete and documented.

- This plan-of-action is approved.

- The Authorization Authority has declared the task/activity is ready to start/restart and operate safely.

ATTACHMENT D - LEVEL 1 AND LEVEL 2 READINESS ASSESSMENT IMPLEMENTATION PLAN

A separate Implementation Plan is NOT required for a level 3 RA.  In this case, the POA will suffice to define the scope and depth of the RA.

The review team responsible for conducting the independent review develops the Implementation Plan.  The Implementation Plan documents not only the process by which the team conducts the review, but also defines the rationale for that process.  The documentation includes the selection of criteria and review approaches and the procedures by which the team will develop findings, observations, conclusions, and the criteria to be applied to categorize findings as pre-start and post-start.  The Implementation Plan is the document that provides the depth of the evaluation of the RA breadth and execution of other details in the approved POA.  The combination of the breadth and depth forms the envelope or scope of the review.  The Implementation Plan should specify the scope for the RA including breadth and depth.

Proper use of the graded approach is essential to conducting a successful RA.  The supporting principle governing the use of the graded approach should be that knowledgeable personnel analyze the factors surrounding the startup or restart, determine the depth of the review needed, and then document the review.  Precise documentation will facilitate communication with knowledgeable outside officials, ensuring the proper level of review has been conducted and that readiness to operate has been accurately verified.  The depth of an RA cannot be determined using a cookbook or formula approach.  Depth requirements depend on knowledgeable people identifying the depth based on their experience, the facility's characteristics, the facility's operating environment, the operating and support organizations capabilities, and the risks associated with the proposed startup or restart.  Further discussion on the graded approach can be found at the Operational Readiness group web page.

The Implementation Plan provides sufficient detail to serve as both information to management and guidance to the team members.  The team preparing the Implementation Plan requires an understanding of the facility and its associated issues.  Pre-development on-site facility visits and interviews may be required before the Implementation Plan can be adequately developed.

As a minimum, the Implementation Plan will confirm personnel, procedures, and equipment important to safety are in a state of readiness to support safe start-up and operation of the facility.  This includes performance demonstration under normal and upset conditions, compliance to approved procedures that implement Technical Safety Requirements testing of equipment to authorization basis, and design requirements that have been completed satisfactorily.

The assessment approaches used and results of this evaluation will be included in the final report.

The Manager, Operational Readiness, will provide the forms required for the assessment to provide consistency.

Lessons learned from previous reviews are reviewed.  The Manager, Operational Readiness, maintains lessons learned.

ATTACHMENT D – Level 1 AND Level 2 Readiness Assessment Implementation Plan (cont.)

The following outline provides a suggested format for the Implementation Plan.  Further details on the Implementation Plan can be found in DOE-STD-3006-2000, Sections 4.2.4, 5.1.4, 5.9.2, and Appendixes 1 and 2.

a.	Introduction/Background:  Describes the activity that will be reviewed and the reason for shutdown (if a restart).  This section provides background information concerning the basic process, hazards, and issues associated with the activity to be reviewed.

b.	Purpose:  Describes the reasons why the RA will be conducted and provides the basic insights for the scope of the review.

c.	Scope:  Defines the physical and administrative boundaries of the facility and justifies those defined boundaries and the support function review relative to each of the following:

- Plant equipment (hardware) readiness

- Management and personnel readiness, and

- Management programs (procedures, plans, etc.) readiness.

The scope section should define the major objectives of the assessment.  These objectives define the discipline or areas that are selected for assessment and define the approach and guidelines that must be implemented for an organization to achieve a state of readiness.

The scope section should describe the breadth from the approved POA.  Each breadth element required by the POA must be incorporated into the Implementation Plan.  The depth to which each scope element is evaluated is specified and quantified by the Implementation Plan criteria and review approaches to be consistent with the discussion in the approved POA.

d.	Prerequisites:  Summarizes the prerequisites specified in the approved POA.  It is not the responsibility of the review team to develop the prerequisites, but they must understand them and be prepared to verify that the prerequisites have been achieved at the start of the RA.

e.	Overall Approach:  Defines the generic approach by which the RA will be conducted and provides an introduction to the assessment process.  The process described in this section will define the criteria and review approaches.  The definition of the criteria by which findings will be classified as pre-start and post-start should be defined here, as should the method for report preparation, finding and observation resolution, and methods for closure.  Include how the team will assess the implementation or integration of the contractor Integrated Safety Management System.

Termination Criteria - If the team (with concurrence of the review team leader) or the review team leader decides the facility is not ready during the RA, stop the RA and provide a letter to the Contractor Authorization Authority detailing the reason(s) for stopping the RA.  Some examples of "Termination Criteria" are; Authorization Basis not approved, Authorization Basis not implemented, programmatic deficiencies in Conduct of Operations implementation, and programmatic procedure deficiencies.

ATTACHMENT D – Level 1 AND Level 2 Readiness Assessment Implementation Plan (cont.)

f.	Readiness Assessment Preparations:  Describes any preparations, including team pre-review site visits, document reviews, etc., that will be undertaken before the on-site review.  A discussion of qualifications and training considerations for team members should appear here.

g.	Readiness Assessment Process:  Describes the actual criteria and review approaches that will be used to assess the defined Core Requirements of the RA.  These criteria and review approaches should include the following items:

Core Requirement/Functional Area - Identification of the requirement that will be verified as having been achieved by the readiness process.

Criteria - The specifics by which the Core Requirements will be measured, which may include regulatory requirements, etc.

Review Approach - A definition of what combination of documentation reviews, personnel interviews, system walk-downs, and exercise and/or drill observations that will be conducted to derive objective evidence by which the team will measure the defined criteria and assess the readiness of the particular objective.

Basis - A discussion of why the particular review is needed.

References - Those requirements or regulatory standards that apply to the Core Requirements and safety documentation that contains the requirements associated with a particular Core Requirement.

Additionally, describe the process to be used to assess the implementation or integration of the contractor Integrated Safety Management System (ISMS).

h.	Administration:  Describes the mechanism for the RA-related meetings, correspondence, communications, team structure, etc., of the review.  The review team composition/organization, interface requirements, any oversight groups, and DOE organizations to be involved in the RA should be discussed in this section.

- Reporting and Resolutions:  This section should detail the methods that the review team will use to report assessment results, including dissenting opinions.

- Schedule:  A discussion of the proposed schedule for any preparation, pre-review site visits, on-site review, conduct of review, report preparation, and closeout.

ATTACHMENT D – Level 1 AND Level 2 Readiness Assessment Implementation Plan (cont.)

k.	Appendixes:  The appendixes should include the affidavits or other specific criteria evaluation and review documents that will be used by the team members to conduct the individual assessments.  They may also include reporting forms, writing guides, and other sections appropriate to stand alone in an appendix.  The appendixes of DOE-STD-3006-2000 contain information and examples that may be useful during development of the appendixes for the Implementation Plan.  As a minimum, the following should be included:

a.	Team members and assignments/areas of review

b.	Applicable Core Requirements and review approaches

c.	Assessment Form (Form 1)

d.	Deficiency Form (Form 2)

e.	Pre-start/post-start item evaluation criteria form.

These forms will be obtained from the Manager, Operational Readiness, to provide consistency.

The numbering sequence for Deficiency Forms will be annotated in the following manner to provide consistency and allow for tracking between reviews:

Finding			CR#-F-00 (sequential #)

Observation		CR#-O-00 (sequential #)

ATTACHMENT E - PRE-START/POST-START ITEM EVALUATION CRITERIA

Figure E-1.  Pre-Start/Post-Start Item Evaluation Criteria.

ITEM: _________________________________________________________________________

This checklist will be used to evaluate whether an item may be resolved after startup or restart.

A.	Initial Screening

Does this item:

1.	Involve a safety system?

YES ___	NO ___

2.	Involve processes, functions, or components identified in the technical safety requirements?

YES ___	NO ___

3.	Involve potential adverse environmental impact exceeding regulatory/site-specific release limits?

YES ___	NO ___

4.	Involve a process, function, or component which implements an approval condition(s) in a permit issued by a regulator?

YES ___	NO ___

5.	Impact non-safety processes, functions, or components which could adversely impact safety related processes, functions, or components?

YES ___	NO ___

6.	Impact worker health and safety?

YES ___	NO ___

7.	Indicate a lack of adequate operating procedures?

YES ___	NO ___

8.	Indicate noncompliance with important procedures?

YES ___	NO ___

9.	Require important operator training not specified in existing facility training requirements?

YES ___	NO ___

ATTACHMENT E - PRE-START/POST-START ITEM EVALUATION CRITERIA (cont.)

Figure E-1.  Pre-Start/Post-Start Item Evaluation Criteria.  (cont.)

ITEM: ____________________________________________________________________________

10.	Impact the performance of the facility mission?

YES ___	NO ___

If the response to any of the above is “YES”, then continue the evaluation below (B. Item Impact).  If the response to the above is “NO”, the item may be resolved after startup or restart (post-start).

B.	Item Impact

Does the loss of operability:

1.	Prevent safe shutdown or cause the loss of essential monitoring?

YES ___	NO ___

2.	Require operator action to prevent or mitigate the consequences of events described in the Facility Safety Analysis Report, HNF-SD-WM-SAR-067, Rev 0?

YES ___	NO ___

3.	Cause operation outside the technical safety requirements?

YES ___	NO ___

4.	Result in a reduction of the margin of safety as described in the Facility Safety Analysis Report?

YES ___	NO ___

Does the item:

5.	Indicate a lack of control, which can have a near-term impact on the operability or functionality of safety-related systems?

YES ___	NO ___

6.	Result in an unacceptable impact on worker safety or health?

YES ___	NO ___

7.	Prevent the facility from performing its mission?

YES ___	NO ___

ATTACHMENT E - PRE-START/POST-START ITEM EVALUATION CRITERIA (cont.)

Figure E-1.  Pre-Start/Post-Start Item Evaluation Criteria.  (cont.)

ITEM: _____________________________________________________________________________

8.	Implement a control required in the Facility Safety Analysis Report?

YES ___	NO ___

If the response to any of the above questions is “YES,” the item is to be considered a pre-start item.  If the response to the above is “NO,” the item should generally be considered post-start.  However, some post-start items may be changed to pre-start by the review team leader because of potential health, safety, and/or environmental significance.

Recommendation:	[   ]  Pre-Start Item	[   ]  Post Start Item

Completed by: ________________________________	________________

Review Team Leader			Date

APPROVAL:	_______________________________	________________

Review Team Leader			Date

_______________________________

Title

ATTACHMENT F - EVALUATION AND TRACKING OF OPEN ITEMS

This attachment defines the process for evaluation and tracking of issues identified during RA activities.  That process will begin during the facility major system acquisition and carry through to final verification and closure of all required items at the point where startup/restart occurs.

During the major system acquisition, on-going preparations are underway to validate and verify the personnel, procedures, equipment, and management control systems associated with the facility startup/restart.  During these activities, items discovered should be categorized as pre-start or post-start according to the information contained in Attachment E, Figure E-1.  The items should be consolidated on an open items list (“list”) and that “list” should be accurately maintained and kept up-to-date.  In addition, the Finding and Resolution Form (Form 3) will be used by the responsible individuals to document the open items and define the corrective actions needed to resolve the final post-start findings.

A determination is made using the pre-start/post-start item evaluation criteria outlined in Attachment E as to whether Non-Readiness Review open items are to be considered pre-start or post-start. The Contractor Authorization Authority or delegate must concur with the determination.

As the facility continues to progress through Contractor RA activities and DOE RA activities, the Director responsible for the activity should provide continual monitoring and tracking of open items and ensure that all appropriate items are incorporated into the “list.”  The final reports from the Contractor RA and the DOE RA activities should be reviewed and reconciled to the “list” to ensure that all items have been entered.

RA findings (both pre-start and post-start) must be documented on the Finding and Resolution Form (Form 3) and processed in accordance with TFC-ESHQ-Q_C-C-01.  Post-start findings will have a corrective action plan.  The Director responsible for the activity should continue to monitor, track, and bring to closure as many items as possible before startup/restart.

Following completion of the last RA activity, the Director responsible for the activity should update and verify a consolidated “list” of pre-start open items from any source, including major system acquisition items, readiness reviews, official acceptance of construction pre-start items, project punch-list pre-start items, as well as any open items that arise during on-going facility startup/restart preparations.

To ensure that no significant issue is overlooked, the Director responsible for the activity should also review all open applicable non-conformance reports, Problem Evaluation Requests (PER), and action items generated since the startup Management Self-Assessment, and open Work Control System items pertaining to the facility or activity undergoing RA.  This consolidated “list” remains under scrutiny as progress is made toward startup/restart.

Immediately before startup/restart, the Director responsible for the activity will verify closure of all pre-start items on the consolidated “list.”  The Director responsible for the activity assembles the verification documentation to support the closure of items in the Readiness Review Certification Package.

ATTACHMENT G - READINESS ASSESSMENT FINAL REPORT FORMAT

The product of a RA is the final report.  It documents the logic of the RA, conveys the results, explains any deviations from the Implementation Plan, and provides the conclusions and findings from the RA along with the process by which they were developed.  The RA final report is the basis for the Contractor Authorization Authority to forward the Readiness to Proceed Memorandum to DOE or if allowed by Startup Notification Report, to approve startup/restart.

The conclusion as to whether the startup/restart of the nuclear facility can proceed safely should be based on the following:

1.	Review of the program to document conformance with the agreed-upon set of requirements, 	including a process to address new requirements.

2.	Extensive use of references to the established requirements in the RA documentation.

Further details on the final report can be found in DOE-STD-3006-2000, Sections 5.1.11, 5.6, and 5.9.3.

A level 1 or level 2 RA final report should follow the format below:

NOTE:  A level 3 RA final report should be in the form of an executive summary, as outlined below.

1.	Title Page (cover)

2.	Signature Page

3.	Table of Contents

4.	Executive Summary

5.	Introduction

6.	Assessment Evaluation

7.	ISMS

8.	Lessons Learned

9.	Appendixes

Title Page:  State the subject and date of the review.  The report cover should be as clean as possible, and should not contain any extraneous information, data, graphs, or pictures.

Signature Page:  Contains the signatures of team members.  It signifies the agreement of the team members as to the report content and conclusions in their assigned area(s).  If the team member signature cannot be obtained due to logistical considerations, the team leader should gain their concurrence via fax or telecom and sign for them.

Table of Contents:  Self-explanatory.

ATTACHMENT G – Readiness Assessment Final Report FORMAT (cont.)

Executive Summary:  A one-to-three page synopsis of the RA, findings, and readiness determination. It is to introduce information and direct readers to those portions of the report that provide more detail concerning the information.  Some suggested points to be considered include:

- A brief synopsis of the RA activities that provide information concerning the team’s evaluation of readiness.

- The readiness of the activity to proceed.

- The management systems adequacy to oversee the operations.

- The implementation or integration of Integrated Safety Management System.

- A summary evaluation of the adequacy of the RA preparation.

- A synopsis of the significant problems and significant strengths.

g.	For a level 3 RA only:  Team member roster with a qualification statement signed by the review team leader stating, as an example, “Verified each team member’s qualifications as adequate.”

Introduction:  Provide information and background regarding the facility being reviewed, the reason(s) for shutdown (if a restart), the purpose of the review, and the scope of the activity evaluated.  Other information that should be provided includes a brief discussion of:

a.	The overall objectives of the review.

b.	The assessment process and methodologies used in the review.

c.	The team composition.

d.	Definitions applicable to the assessment.

Assessment Evaluation:  For each Core Requirement, the report must document the RA logic, discuss the Core Requirement and provide conclusions as to the readiness for each major area.  Conclusions as to the readiness of the hardware, personnel, procedures, and management systems that control each RA area should be addressed, including key issues concerning the RA area.  The evaluation should discuss the pre-start and post-start findings associated with the RA, explain how these findings relate to the conclusion of each area and the RA as a hole, and provide a conclusion as to the readiness of the facility to begin operations.  Additionally, the status of compliance to orders within the scope of the RA is discussed, and in the opinion of the RA team, adequately provide for the protection of the public health, worker safety, and the environment.

This section should also provide for “differing opinions.”  While the team should strive to reach consensus concerning the aspects of the RA, professional judgment does not always allow for complete agreement.  In the case of disagreement, the team leader must make the final decision concerning the disposition of the finding.  However, discussion of the aspects will be provided in the report to allow the authorization authority the relevant information on which to make a decision.  If a team member feels that aspects of their opinions have not been adequately represented, the member will file a report of differing opinion.  This report is attached to the final report.

ATTACHMENT G – Readiness Assessment Final Report FORMAT (cont.)

Any deviations from the Implementation Plan should be discussed, along with the reason for the deviation(s), and what alternate actions were taken to compensate, if required.  As the evaluation sections provide the basis for the determination of readiness for each Core Requirement, it should discuss not only the deficiencies but also the positive aspects determined.  The detailed documentation to support the conclusions should be included in the appendixes.

Status of Integrated Safety Management System (ISMS) Implementation:  Statements related to an assessment of the adequacy of the implementation of the Core Requirements and, thereby, the ISMS Guiding Principles.  The extent that the ISMS principles were visible in the RA should be evaluated and reported.

Lessons Learned:  The report should identify Lessons Learned that may be applied to design, construction, operations, and decommissioning similar facilities and to future reviews.  The report should address the problems and successes encountered in the RA (what worked and what did not).

Appendixes:  Provides for the data that supports the RA.  Data that should be considered include:

a.	Implementation Plan.

b.	Criteria and review approaches.

c.	Assessment activity plan.

d.	Team member roster.

NOTE:  A level 1 and level 2 RA requires a team member roster with a qualification bio or summary for each team member.

e.	Evaluation criteria.

f.	Pre-start issue summary.

g.	Post-start issue summary.